## End-to-End Master Plan
Module | Task | Component | Dependency | Estimates (Days) | Resource | Planned Start Date | Planned End Date | Milestone
All Modules | Unified UI Wireframe & UX Research | UI | Project Start | 6 | UX Designer | 06-Jan-2026 | 11-Jan-2026
| Wireframe Review & Sign-off | UI | Unified UI Wireframe & UX Research | 4 | UX + Stakeholders | 12-Jan-2026 | 16-Jan-2026 | UX Baseline Approved
Module 1: User Management & Security | Auth Strategy & RBAC Design | Backend | Project Start | 5 | Backend Architect | 10-Jan-2026 | 15-Jan-2026
| Auth APIs & Middleware | Backend | Auth Strategy & RBAC Design | 18 | Backend Team | 16-Jan-2026 | 10-Feb-2026
| User / Role / Login UI | UI | UX Baseline Approved | 15 | UI Team | 17-Jan-2026 | 07-Feb-2026
| QA Test Scenario & Test Case Design | QA | Auth Strategy & RBAC Design | 5 | QA Team | 15-Jan-2026 | 20-Jan-2026
| QA Functional Testing | QA | Auth APIs & Middleware | 7 | QA Team | 25-Jan-2026 | 02-Feb-2026
| QA Bug Retest & Regression | QA | QA Functional Testing | 3 | QA Team | 03-Feb-2026 | 07-Feb-2026 | Module 1 Complete
Module 2: API Connector Master | Connector Model & Token Logic | Backend | Project Start | 14 | Backend Team | 20-Jan-2026 | 08-Feb-2026
| API Connector UI | UI | UX Baseline Approved | 12 | UI Team | 01-Feb-2026 | 17-Feb-2026
| QA Test Scenario & Data Preparation | QA | Connector Model & Token Logic | 4 | QA Team | 01-Feb-2026 | 05-Feb-2026
| QA Functional & Integration Testing | QA | API Connector UI | 6 | QA Team | 10-Feb-2026 | 18-Feb-2026
| QA Bug Retest & Stabilization | QA | QA Functional & Integration Testing | 2 | QA Team | 19-Feb-2026 | 21-Feb-2026 | Module 2 Complete
Module 3: DB Connector Master | DB Connector Backend & Pooling | Backend | Project Start | 14 | Backend Team | 01-Feb-2026 | 20-Feb-2026
| DB Connector UI | UI | UX Baseline Approved | 10 | UI Team | 15-Feb-2026 | 28-Feb-2026
| QA Test Case Design & Query Validation | QA | DB Connector Backend & Pooling | 4 | QA Team | 15-Feb-2026 | 19-Feb-2026
| QA Functional & Data Accuracy Testing | QA | DB Connector UI | 6 | QA Team | 21-Feb-2026 | 28-Feb-2026
| QA Bug Retest & Regression | QA | QA Functional & Data Accuracy Testing | 2 | QA Team | 01-Mar-2026 | 03-Mar-2026 | Module 3 Complete
Module 4: Test Case Management | Test Case CRUD & Versioning APIs | Backend | Module 2 Complete | 20 | Backend Team | 10-Feb-2026 | 10-Mar-2026
| Test Case Management UI | UI | UX Baseline Approved | 18 | UI Team | 20-Feb-2026 | 15-Mar-2026
| QA Test Case Design & Rule Matrix | QA | Test Case CRUD & Versioning APIs | 5 | QA Team | 05-Mar-2026 | 10-Mar-2026
| QA Functional & UI Validation | QA | Test Case Management UI | 7 | QA Team | 11-Mar-2026 | 20-Mar-2026
| QA Bug Retest & Version Validation | QA | QA Functional & UI Validation | 3 | QA Team | 21-Mar-2026 | 31-Mar-2026 | Test Case Creation Ready
Module 5: Bulk Test Case Import | Import Template Design (CSV/Excel) | Backend | Test Case Creation Ready | 5 | Backend + QA | 01-Apr-2026 | 05-Apr-2026 | Template Finalized
| Bulk Import Parser & Validation | Backend | Import Template Design (CSV/Excel) | 10 | Backend Team | 06-Apr-2026 | 18-Apr-2026
| Bulk Import UI | UI | UX Baseline Approved | 8 | UI Team | 05-Apr-2026 | 18-Apr-2026
| QA Template Review & Test Data Prep | QA | Import Template Design (CSV/Excel) | 3 | QA Team | 03-Apr-2026 | 05-Apr-2026
| QA Bulk Import Functional Testing | QA | Bulk Import Parser & Validation | 4 | QA Team | 19-Apr-2026 | 24-Apr-2026
| QA Bug Retest & Partial Success Validation | QA | QA Bulk Import Functional Testing | 2 | QA Team | 25-Apr-2026 | 30-Apr-2026 | Bulk Import Ready
Module 6: Test Execution Engine | Execution Engine Core Services | Backend | Module 4 Complete | 20 | Backend Team | 01-Mar-2026 | 30-Mar-2026
| Execution Trigger & Status UI | UI | UX Baseline Approved | 12 | UI Team | 15-Mar-2026 | 30-Mar-2026
| QA Test Scenario Design (Execution Flow) | QA | Execution Engine Core Services | 4 | QA Team | 20-Mar-2026 | 25-Mar-2026
| QA Execution & Parallel Run Testing | QA | Execution Trigger & Status UI | 7 | QA Team | 01-Apr-2026 | 10-Apr-2026
| QA Bug Retest & Stability Validation | QA | QA Execution & Parallel Run Testing | 4 | QA Team | 11-Apr-2026 | 20-Apr-2026 | Execution Engine Stable
Module 7: Test Pack & Scheduling | Scheduler & Pack Mapping APIs | Backend | Execution Engine Stable | 10 | Backend Team | 01-Apr-2026 | 15-Apr-2026
| Test Pack UI & Scheduling | UI | UX Baseline Approved | 8 | UI Team | 05-Apr-2026 | 15-Apr-2026
| QA Scheduling Scenario Design | QA | Scheduler & Pack Mapping APIs | 3 | QA Team | 10-Apr-2026 | 12-Apr-2026
| QA Schedule Execution Testing | QA | Test Pack UI & Scheduling | 3 | QA Team | 16-Apr-2026 | 20-Apr-2026
| QA Bug Retest & Retry Validation | QA | QA Schedule Execution Testing | 2 | QA Team | 21-Apr-2026 | 25-Apr-2026 | Scheduling Ready
Module 8: Validation Engine | Validation Rule Engine & DB Compare | Backend | Execution Engine Stable | 14 | Backend Team | 10-Apr-2026 | 30-Apr-2026
| QA Rule Coverage & Expected Data Prep | QA | Validation Rule Engine & DB Compare | 4 | QA Team | 25-Apr-2026 | 30-Apr-2026
| QA Validation Accuracy Testing | QA | QA Rule Coverage & Expected Data Prep | 4 | QA Team | 01-May-2026 | 06-May-2026
| QA Bug Retest & Rule Stabilization | QA | QA Validation Accuracy Testing | 4 | QA Team | 07-May-2026 | 12-May-2026 | Validation Engine Ready
Module 9: HTML Report & Audit | HTML Report & Audit APIs | Backend | Validation Engine Ready | 10 | Backend Team | 15-Apr-2026 | 30-Apr-2026
| Report View UI & Export | UI | UX Baseline Approved | 8 | UI Team | 18-Apr-2026 | 30-Apr-2026
| QA Report Structure & Data Mapping Review | QA | HTML Report & Audit APIs | 3 | QA Team | 25-Apr-2026 | 28-Apr-2026
| QA Report Functional & Export Testing | QA | Report View UI & Export | 3 | QA Team | 01-May-2026 | 06-May-2026
| QA Bug Retest & Audit Validation | QA | QA Report Functional & Export Testing | 2 | QA Team | 07-May-2026 | 12-May-2026 | Reporting Ready
Module 10: Execution Dashboard | Execution Aggregation APIs | Backend | HTML Report & Audit APIs | 10 | Backend Team | 20-Apr-2026 | 05-May-2026
| Execution Dashboard UI | UI | UX Baseline Approved | 8 | UI Team | 25-Apr-2026 | 05-May-2026
| QA Dashboard Metric Validation | QA | Execution Aggregation APIs | 3 | QA Team | 01-May-2026 | 04-May-2026
| QA Dashboard UI & Data Testing | QA | Execution Dashboard UI | 3 | QA Team | 06-May-2026 | 10-May-2026
| QA Bug Retest & Trend Validation | QA | QA Dashboard UI & Data Testing | 2 | QA Team | 11-May-2026 | 15-May-2026 | Dashboard Ready
Module 11: Test Coverage Dashboard | Coverage Calculation APIs | Backend | Test Case Creation Ready | 8 | Backend Team | 25-Apr-2026 | 05-May-2026
| Coverage Dashboard UI | UI | UX Baseline Approved | 8 | UI Team | 01-May-2026 | 10-May-2026
| QA Coverage Rule Mapping Review | QA | Coverage Calculation APIs | 3 | QA Team | 06-May-2026 | 08-May-2026
| QA Coverage Accuracy Testing | QA | Coverage Dashboard UI | 3 | QA Team | 11-May-2026 | 15-May-2026
| QA Bug Retest & Coverage Stabilization | QA | QA Coverage Accuracy Testing | 2 | QA Team | 16-May-2026 | 20-May-2026 | Coverage Ready
Module 12: Configuration Master Data | Master Data CRUD & RBAC APIs | Backend | Module 1 Complete | 12 | Backend Team | 20-Apr-2026 | 05-May-2026
| Configuration Screens UI | UI | UX Baseline Approved | 10 | UI Team | 25-Apr-2026 | 10-May-2026
| QA Master Data Scenario Design | QA | Master Data CRUD & RBAC APIs | 3 | QA Team | 05-May-2026 | 07-May-2026
| QA CRUD & RBAC Validation | QA | Configuration Screens UI | 3 | QA Team | 11-May-2026 | 15-May-2026
| QA Bug Retest & Regression | QA | QA CRUD & RBAC Validation | 2 | QA Team | 16-May-2026 | 20-May-2026 | Configuration Ready
All Modules | End-to-End Regression, Bug Retest & Go-Live Validation | QA | All Modules Ready | 10 | QA Team | 21-May-2026 | 31-May-2026 | System Go-Live