## End-to-End Master Plan
Module | Task | Component | Dependency | Estimates (Days) | Resource | Planned Start Date | Planned End Date | Milestone
All Modules | Unified UI Wireframe & UX Research | UI | Project Start | 6 | UX Designer | 06-Jan-2026 | 46035
All Modules | KT Sessions to New Resources | Cross-Team | UX Baseline Approved | 5 | Leads (Backend/UI/QA) | 19-Jan-2026 | 46045 | KT Completed
All Modules | Wireframe Review & Sign-off | UI | Unified UI Wireframe & UX Research | 4 | UX + Stakeholders | 12-Jan-2026 | 46037 | UX Baseline Approved
Module 1: API Connector Master | System Analysis | Backend | Development Kickoff | 3 | Backend Architect | 03-Feb-2026 | 46058
Module 1: API Connector Master | Connector Module Implementation | Backend | System Analysis | 5 | Backend Team | 03-Feb-2026 | 46062
Module 1: API Connector Master | Token Logic Implementation | Backend | Connector Module Implementation | 4 | Backend Team | 03-Feb-2026 | 46059
Module 1: API Connector Master | Connector Model & Token Logic | Backend | Development Kickoff | 14 | Backend Team | 03-Feb-2026 | 46073
Module 1: API Connector Master | API Connector UI | UI | UX Baseline Approved | 12 | UI Team | 03-Feb-2026 | 46071
Module 1: API Connector Master | QA Test Scenario & Data Preparation | QA | Connector Model & Token Logic | 4 | QA Team | 03-Feb-2026 | 46059
Module 1: API Connector Master | QA Functional & Integration Testing | QA | API Connector UI | 6 | QA Team | 03-Feb-2026 | 46063
Module 1: API Connector Master | Backend Bug Fixing | Backend | QA Functional Testing | 3 | Backend Team | 03-Feb-2026 | 46058
Module 1: API Connector Master | UI Bug Fixing | UI | QA Functional Testing | 2 | UI Team | 03-Feb-2026 | 46057
Module 1: API Connector Master | QA Bug Retest & Stabilization | QA | Backend Bug Fixing & UI Bug Fixing | 2 | QA Team | 03-Feb-2026 | 46057 | Module 2 Complete
Module 2: DB Connector Master | System Analysis | Backend | Development Kickoff | 3 | Backend Architect | 01-Feb-2026 | 46056
Module 2: DB Connector Master | Connector Module Implementation | Backend | System Analysis | 5 | Backend Team | 01-Feb-2026 | 46058
Module 2: DB Connector Master | Token Logic Implementation | Backend | Connector Module Implementation | 4 | Backend Team | 01-Feb-2026 | 46057
Module 2: DB Connector Master | DB Connector Backend & Pooling | Backend | Development Kickoff | 14 | Backend Team | 01-Feb-2026 | 46071
Module 2: DB Connector Master | DB Connector UI | UI | UX Baseline Approved | 10 | UI Team | 15-Feb-2026 | 46079
Module 2: DB Connector Master | QA Test Case Design & Query Validation | QA | DB Connector Backend & Pooling | 4 | QA Team | 15-Feb-2026 | 46071
Module 2: DB Connector Master | QA Functional & Data Accuracy Testing | QA | DB Connector UI | 6 | QA Team | 21-Feb-2026 | 46080
Module 2: DB Connector Master | Backend Bug Fixing | Backend | QA Functional Testing | 3 | Backend Team | 01-Mar-2026 | 46084
Module 2: DB Connector Master | UI Bug Fixing | UI | QA Functional Testing | 2 | UI Team | 01-Mar-2026 | 46083
Module 2: DB Connector Master | QA Bug Retest & Regression | QA | Backend Bug Fixing & UI Bug Fixing | 2 | QA Team | 01-Mar-2026 | 46083 | Module 3 Complete
Module 3: Test Case Management | Test Case CRUD & Versioning APIs | Backend | Module 2 Complete | 20 | Backend Team | 10-Feb-2026 | 46091
Module 3: Test Case Management | Test Case Management UI | UI | UX Baseline Approved | 18 | UI Team | 20-Feb-2026 | 46099
Module 3: Test Case Management | QA Test Case Design & Rule Matrix | QA | Test Case CRUD & Versioning APIs | 5 | QA Team | 05-Mar-2026 | 46092
Module 3: Test Case Management | QA Functional & UI Validation | QA | Test Case Management UI | 7 | QA Team | 11-Mar-2026 | 46100
Module 3: Test Case Management | Backend Bug Fixing | Backend | QA Functional Testing | 3 | Backend Team | 21-Mar-2026 | 46105
Module 3: Test Case Management | UI Bug Fixing | UI | QA Functional Testing | 2 | UI Team | 21-Mar-2026 | 46104
Module 3: Test Case Management | QA Bug Retest & Version Validation | QA | Backend Bug Fixing & UI Bug Fixing | 3 | QA Team | 21-Mar-2026 | 46105 | Test Case Creation Ready
Module 4: Bulk Test Case Import | Import Template Design (CSV/Excel) | Backend | Test Case Creation Ready | 5 | Backend + QA | 01-Apr-2026 | 46119 | Template Finalized
Module 4: Bulk Test Case Import | Bulk Import Parser & Validation | Backend | Import Template Design (CSV/Excel) | 10 | Backend Team | 06-Apr-2026 | 46129
Module 4: Bulk Test Case Import | Bulk Import UI | UI | UX Baseline Approved | 8 | UI Team | 05-Apr-2026 | 46126
Module 4: Bulk Test Case Import | QA Template Review & Test Data Prep | QA | Import Template Design (CSV/Excel) | 3 | QA Team | 03-Apr-2026 | 46119
Module 4: Bulk Test Case Import | QA Bulk Import Functional Testing | QA | Bulk Import Parser & Validation | 4 | QA Team | 19-Apr-2026 | 46134
Module 4: Bulk Test Case Import | Backend Bug Fixing | Backend | QA Functional Testing | 3 | Backend Team | 25-Apr-2026 | 46140
Module 4: Bulk Test Case Import | UI Bug Fixing | UI | QA Functional Testing | 2 | UI Team | 25-Apr-2026 | 46139
Module 4: Bulk Test Case Import | QA Bug Retest & Partial Success Validation | QA | Backend Bug Fixing & UI Bug Fixing | 2 | QA Team | 25-Apr-2026 | 46139 | Bulk Import Ready
Module 5: Test Execution Engine | Execution Engine Core Services | Backend | Module 4 Complete | 20 | Backend Team | 01-Mar-2026 | 46108
Module 5: Test Execution Engine | Execution Trigger & Status UI | UI | UX Baseline Approved | 12 | UI Team | 15-Mar-2026 | 46111
Module 5: Test Execution Engine | QA Test Scenario Design (Execution Flow) | QA | Execution Engine Core Services | 4 | QA Team | 20-Mar-2026 | 46106
Module 5: Test Execution Engine | QA Execution & Parallel Run Testing | QA | Execution Trigger & Status UI | 7 | QA Team | 01-Apr-2026 | 46121
Module 5: Test Execution Engine | Backend Bug Fixing | Backend | QA Functional Testing | 3 | Backend Team | 11-Apr-2026 | 46126
Module 5: Test Execution Engine | UI Bug Fixing | UI | QA Functional Testing | 2 | UI Team | 11-Apr-2026 | 46125
Module 5: Test Execution Engine | QA Bug Retest & Stability Validation | QA | Backend Bug Fixing & UI Bug Fixing | 4 | QA Team | 11-Apr-2026 | 46127 | Execution Engine Stable
Module 6: Test Pack & Scheduling | Scheduler & Pack Mapping APIs | Backend | Execution Engine Stable | 10 | Backend Team | 01-Apr-2026 | 46126
Module 6: Test Pack & Scheduling | Test Pack UI & Scheduling | UI | UX Baseline Approved | 8 | UI Team | 05-Apr-2026 | 46126
Module 6: Test Pack & Scheduling | QA Scheduling Scenario Design | QA | Scheduler & Pack Mapping APIs | 3 | QA Team | 10-Apr-2026 | 46126
Module 6: Test Pack & Scheduling | QA Schedule Execution Testing | QA | Test Pack UI & Scheduling | 3 | QA Team | 16-Apr-2026 | 46132
Module 6: Test Pack & Scheduling | Backend Bug Fixing | Backend | QA Functional Testing | 3 | Backend Team | 21-Apr-2026 | 46135
Module 6: Test Pack & Scheduling | UI Bug Fixing | UI | QA Functional Testing | 2 | UI Team | 21-Apr-2026 | 46134
Module 6: Test Pack & Scheduling | QA Bug Retest & Retry Validation | QA | Backend Bug Fixing & UI Bug Fixing | 2 | QA Team | 21-Apr-2026 | 46134 | Scheduling Ready
Module 8: Validation Engine | Sample Input & Expected Output File Preparation (UK Region) | QA | HSBC SME Input Dependency | 5 | HSBC + QA Team | 05-May-2026 | 46153
Module 8: Validation Engine | Sample Input & Expected Output File Preparation (UK Region) | QA | HSBC SME Input Dependency | 5 | HSBC + QA Team | 05-May-2026 | 46153
Module 8: Validation Engine | Validation Rule Engine & DB Compare | Backend | Execution Engine Stable | 14 | Backend Team | 10-Apr-2026 | 46141
Module 8: Validation Engine | QA Rule Coverage & Expected Data Prep | QA | Validation Rule Engine & DB Compare | 4 | QA Team | 25-Apr-2026 | 46141
Module 8: Validation Engine | QA Validation Accuracy Testing | QA | QA Rule Coverage & Expected Data Prep | 4 | QA Team | 01-May-2026 | 46148
Module 8: Validation Engine | Backend Bug Fixing | Backend | QA Functional Testing | 3 | Backend Team | 07-May-2026 | 46153
Module 8: Validation Engine | UI Bug Fixing | UI | QA Functional Testing | 2 | UI Team | 07-May-2026 | 46150
Module 8: Validation Engine | QA Bug Retest & Rule Stabilization | QA | Backend Bug Fixing & UI Bug Fixing | 4 | QA Team | 07-May-2026 | 46154 | Validation Engine Ready
Module 8: HTML Report & Audit | HTML Report & Audit APIs | Backend | Validation Engine Ready | 10 | Backend Team | 15-Apr-2026 | 46140
Module 8: HTML Report & Audit | Report View UI & Export | UI | UX Baseline Approved | 8 | UI Team | 18-Apr-2026 | 46140
Module 8: HTML Report & Audit | QA Report Structure & Data Mapping Review | QA | HTML Report & Audit APIs | 3 | QA Team | 25-Apr-2026 | 46140
Module 8: HTML Report & Audit | QA Report Functional & Export Testing | QA | Report View UI & Export | 3 | QA Team | 01-May-2026 | 46147
Module 8: HTML Report & Audit | Backend Bug Fixing | Backend | QA Functional Testing | 3 | Backend Team | 07-May-2026 | 46153
Module 8: HTML Report & Audit | UI Bug Fixing | UI | QA Functional Testing | 2 | UI Team | 07-May-2026 | 46150
Module 8: HTML Report & Audit | QA Bug Retest & Audit Validation | QA | Backend Bug Fixing & UI Bug Fixing | 2 | QA Team | 07-May-2026 | 46150 | Reporting Ready
Module 9: Execution Dashboard | Execution Aggregation APIs | Backend | HTML Report & Audit APIs | 10 | Backend Team | 20-Apr-2026 | 46146
Module 9: Execution Dashboard | Execution Dashboard UI | UI | UX Baseline Approved | 8 | UI Team | 25-Apr-2026 | 46148
Module 9: Execution Dashboard | QA Dashboard Metric Validation | QA | Execution Aggregation APIs | 3 | QA Team | 01-May-2026 | 46147
Module 9: Execution Dashboard | QA Dashboard UI & Data Testing | QA | Execution Dashboard UI | 3 | QA Team | 06-May-2026 | 46150
Module 9: Execution Dashboard | Backend Bug Fixing | Backend | QA Functional Testing | 3 | Backend Team | 11-May-2026 | 46155
Module 9: Execution Dashboard | UI Bug Fixing | UI | QA Functional Testing | 2 | UI Team | 11-May-2026 | 46154
Module 9: Execution Dashboard | QA Bug Retest & Trend Validation | QA | Backend Bug Fixing & UI Bug Fixing | 2 | QA Team | 11-May-2026 | 46154 | Dashboard Ready
Module 10: Test Coverage Dashboard | Coverage Calculation APIs | Backend | Test Case Creation Ready | 8 | Backend Team | 15-May-2026 | 46168
Module 10: Test Coverage Dashboard | Coverage Dashboard UI | UI | UX Baseline Approved | 8 | UI Team | 15-May-2026 | 46168
Module 10: Test Coverage Dashboard | QA Coverage Rule Mapping Review | QA | Coverage Calculation APIs | 3 | QA Team | 15-May-2026 | 46161
Module 10: Test Coverage Dashboard | QA Coverage Accuracy Testing | QA | Coverage Dashboard UI | 3 | QA Team | 15-May-2026 | 46161
Module 10: Test Coverage Dashboard | Backend Bug Fixing | Backend | QA Functional Testing | 3 | Backend Team | 15-May-2026 | 46161
Module 10: Test Coverage Dashboard | UI Bug Fixing | UI | QA Functional Testing | 2 | UI Team | 15-May-2026 | 46160
Module 10: Test Coverage Dashboard | QA Bug Retest & Coverage Stabilization | QA | Backend Bug Fixing & UI Bug Fixing | 2 | QA Team | 15-May-2026 | 46160 | Coverage Ready
Module 11: Health Check & System Monitoring | Health Check API Design & Contract | Backend | Development Kickoff | 3 | Backend Architect | 15-May-2026 | 46161
Module 11: Health Check & System Monitoring | Service-Level Health Check APIs (API/DB/Token) | Backend | Health Check API Design & Contract | 7 | Backend Team | 15-May-2026 | 46167
Module 11: Health Check & System Monitoring | Health Status UI (Optional / Admin View) | UI | UX Baseline Approved | 5 | UI Team | 15-May-2026 | 46163
Module 11: Health Check & System Monitoring | QA Health Scenario Design | QA | Health Check API Design & Contract | 2 | QA Team | 15-May-2026 | 46160
Module 11: Health Check & System Monitoring | QA Health Check Validation | QA | Service-Level Health Check APIs (API/DB/Token) | 4 | QA Team | 15-May-2026 | 46162 | Health Check Ready
Module 12: User Management & Security | Auth Strategy & RBAC Design | Backend | Development Kickoff | 5 | Backend Architect | 15-May-2026 | 46163
Module 12: User Management & Security | Auth APIs & Middleware | Backend | Auth Strategy & RBAC Design | 18 | Backend Team | 15-May-2026 | 46182
Module 12: User Management & Security | User / Role / Login UI | UI | UX Baseline Approved | 15 | UI Team | 15-May-2026 | 46177
Module 12: User Management & Security | QA Test Scenario & Test Case Design | QA | Auth Strategy & RBAC Design | 5 | QA Team | 15-May-2026 | 46163
Module 12: User Management & Security | QA Functional Testing | QA | Auth APIs & Middleware | 7 | QA Team | 15-May-2026 | 46167
Module 12: User Management & Security | Backend Bug Fixing | Backend | QA Functional Testing | 3 | Backend Team | 15-May-2026 | 46161
Module 12: User Management & Security | UI Bug Fixing | UI | QA Functional Testing | 2 | UI Team | 15-May-2026 | 46160
Module 12: User Management & Security | QA Bug Retest & Regression | QA | Backend Bug Fixing & UI Bug Fixing | 3 | QA Team | 15-May-2026 | 46161 | Module 1 Complete
Module 12: Configuration Master Data | Master Data CRUD & RBAC APIs | Backend | Module 1 Complete | 12 | Backend Team | 15-May-2026 | 46174
Module 12: Configuration Master Data | Configuration Screens UI | UI | UX Baseline Approved | 10 | UI Team | 15-May-2026 | 46170
Module 12: Configuration Master Data | QA Master Data Scenario Design | QA | Master Data CRUD & RBAC APIs | 3 | QA Team | 15-May-2026 | 46161
Module 12: Configuration Master Data | QA CRUD & RBAC Validation | QA | Configuration Screens UI | 3 | QA Team | 15-May-2026 | 46161
Module 12: Configuration Master Data | Backend Bug Fixing | Backend | QA Functional Testing | 3 | Backend Team | 15-May-2026 | 46161
Module 12: Configuration Master Data | UI Bug Fixing | UI | QA Functional Testing | 2 | UI Team | 15-May-2026 | 46160
Module 12: Configuration Master Data | QA Bug Retest & Regression | QA | Backend Bug Fixing & UI Bug Fixing | 2 | QA Team | 15-May-2026 | 46160 | Configuration Ready
All Modules | Backend Bug Fixing | Backend | QA Functional Testing | 3 | Backend Team | 15-Jan-2026 | 46041
All Modules | UI Bug Fixing | UI | QA Functional Testing | 2 | UI Team | 15-Jan-2026 | 46038
All Modules | End-to-End Regression, Bug Retest & Go-Live Validation | QA | Backend Bug Fixing & UI Bug Fixing | 10 | QA Team | 18-May-2026 | 46171 | Smoke Test & System Go-Live
All Modules | Pre-Regression Smoke Test using Health Check APIs | QA | Health Check Ready | 3 | QA Team | 18-May-2026 | 46162 | Smoke Test Passed
All Modules | Cross-Module Regression Testing (Post Module 9) | QA | Module 9 Complete | 10 | QA Team | 18-May-2026 | 46171 | Regression Complete
Formulas:
Planned End Date = WORKDAY([Planned Start Date],[Estimates (Days)]-1,Holidays!$A2:A5)

## Holidays
Holiday Date
01-Jan-2026
26-Jan-2026
04-Mar-2026
01-May-2026