## Phase 2
Module | Task | Component | Dependency | Estimates (Days) | Resource | Start | End | Milestone
Module 1: API Connector | System Analysis & Solution Design | Backend | Project Start | 5 | Dev-1 (Lead) | 2026-02-10 | 2026-02-16
| Connector Module Implementation | Backend | Analysis Complete | 5 | Dev-1 (Lead) | 2026-02-17 | 2026-02-23
| Token Logic Implementation | Backend | Connector Impl | 5 | Dev-1 (Lead) | 2026-02-24 | 2026-02-28
| API Connector UI | UI | UX Draft | 6 | UI-1 | 2026-02-18 | 2026-02-25
| QA Scenario & Test Case Design | QA | Req + UX | 4 | QA-1 | 2026-02-18 | 2026-02-23
| QA Test Data Preparation | QA | API Draft | 2 | QA-1 | 2026-02-24 | 2026-02-25
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 2 | Dev-1 + UI-1 | 2026-03-02 | 2026-03-03
| QA Functional Execution | QA | Integration Complete | 4 | QA-1 | 2026-03-04 | 2026-03-09
| Bug Fixing (BE + UI) | Backend/UI | QA Defects | 2 | Dev-3 + UI-1 | 2026-03-10 | 2026-03-11
| QA Retest & Stabilization | QA | Fixes Done | 2 | QA-2 | 2026-03-12 | 2026-03-13 | Module 1 Complete
Module 2: DB Connector | System Analysis & Design | Backend | Parallel M1 | 5 | Dev-2 (Lead) | 2026-02-10 | 2026-02-16
| DB Connector Backend & Pooling | Backend | Analysis | 5 | Dev-2 (Lead) | 2026-02-17 | 2026-02-23
| Token Logic Implementation | Backend | Backend Impl | 5 | Dev-2 (Lead) | 2026-02-24 | 2026-02-28
| DB Connector UI | UI | UX Draft | 6 | UI-1 | 2026-02-20 | 2026-02-27
| QA Scenario & Query Design | QA | Req + DB Model | 4 | QA-1 | 2026-02-18 | 2026-02-23
| QA Test Data & Validation Rules | QA | API Draft | 2 | QA-1 | 2026-02-24 | 2026-02-25
| Integration & Unit Testing | Backend/UI | Backend + UI | 2 | Dev-2 + UI-1 | 2026-03-02 | 2026-03-03
| QA Functional Execution | QA | Integration Complete | 4 | QA-1 | 2026-03-04 | 2026-03-09
| Bug Fixing (BE + UI) | Backend/UI | QA Defects | 2 | Dev-3 + UI-1 | 2026-03-10 | 2026-03-11
| QA Retest & Regression | QA | Fixes Done | 2 | QA-2 | 2026-03-12 | 2026-03-13 | Module 2 Complete
Module 3: Test Case Management | Test Case CRUD & Versioning APIs | Backend | M1 & M2 Done | 7 | Dev-1 (Lead) | 2026-03-18 | 2026-03-26
| Test Case Management UI | UI | UX Draft | 6 | UI-1 | 2026-03-23 | 2026-03-30
| QA Scenario & Coverage Design | QA | Feature Definition | 5 | QA-1 | 2026-03-18 | 2026-03-24
| QA Test Data & Versioning | QA | API Draft | 3 | QA-1 | 2026-03-25 | 2026-03-27
| Integration & Unit Testing | Backend/UI | Backend + UI | 2 | Dev-1 + UI-1 | 2026-03-31 | 2026-04-01
| QA Functional Execution | QA | Integration Complete | 4 | QA-1 | 2026-04-02 | 2026-04-07
| Bug Fixing (BE + UI) | Backend/UI | QA Defects | 2 | Dev-3 + UI-1 | 2026-04-08 | 2026-04-09
| QA Retest & Validation | QA | Fixes Done | 2 | QA-2 | 2026-04-10 | 2026-04-13 | Module 3 Complete
Module 4: Bulk Test Case Import | Import Template Design | Backend | M3 Done | 5 | Dev-2 (Lead) | 2026-04-14 | 2026-04-20
| Bulk Import Parser & Validation | Backend | Template Ready | 5 | Dev-2 (Lead) | 2026-04-21 | 2026-04-27
| Bulk Import UI | UI | UX Draft | 5 | UI-1 | 2026-04-21 | 2026-04-27
| QA Scenario & Template Review | QA | Template Draft | 4 | QA-1 | 2026-04-21 | 2026-04-24
| Integration & Unit Testing | Backend/UI | Backend + UI | 2 | Dev-2 + UI-1 | 2026-04-28 | 2026-04-29
| QA Functional Execution | QA | Integration Complete | 4 | QA-1 | 2026-04-30 | 2026-05-05
| Bug Fixing (BE + UI) | Backend/UI | QA Defects | 2 | Dev-3 + UI-1 | 2026-05-06 | 2026-05-07
| QA Retest & Validation | QA | Fixes Done | 2 | QA-2 | 2026-05-08 | 2026-05-11 | Module 4 Complete
Module 5: Test Execution Engine | Execution Engine Core | Backend | M4 Done | 5 | Dev-1 (Lead) | 2026-04-15 | 2026-04-21
| Execution UI | UI | UX Draft | 4 | UI-1 | 2026-04-16 | 2026-04-21
| QA Scenario & Flow Design | QA | Feature Draft | 4 | QA-1 | 2026-04-16 | 2026-04-21
| Integration & Unit Testing | Backend/UI | Backend + UI | 2 | Dev-1 + UI-1 | 2026-04-22 | 2026-04-23
| QA Execution Testing | QA | Integration Complete | 4 | QA-1 | 2026-04-24 | 2026-04-29
| Bug Fixing & Retest | Backend/UI/QA | QA Defects | 4 | Dev-3 + UI-1 + QA-2 | 2026-04-30 | 2026-05-05 | Module 5 Complete
Module 6: Validation Engine | Validation Rule Engine | Backend | M5 Done | 5 | Dev-2 (Lead) | 2026-04-22 | 2026-04-28
| QA Rule & Data Design | QA | Rule Draft | 4 | QA-1 | 2026-04-22 | 2026-04-25
| Integration & Unit Testing | Backend/UI | Backend Ready | 2 | Dev-2 + UI-1 | 2026-04-29 | 2026-04-30
| QA Validation Execution | QA | Integration Complete | 3 | QA-1 | 2026-05-01 | 2026-05-05
| Bug Fixing & Retest | Backend/UI/QA | QA Defects | 4 | Dev-3 + UI-1 + QA-2 | 2026-05-06 | 2026-05-11 | Module 6 Complete
Module 7: Test Pack & Scheduling | Scheduler & Pack APIs | Backend | M6 Done | 4 | Dev-1 (Lead) | 2026-05-01 | 2026-05-06
| Scheduling UI | UI | UX Draft | 4 | UI-1 | 2026-05-01 | 2026-05-06
| QA Scenario & Execution | QA | Integration Ready | 5 | QA-1 | 2026-05-07 | 2026-05-13
| Bug Fixing & Retest | Backend/UI/QA | QA Defects | 2 | Dev-3 + QA-2 | 2026-05-14 | 2026-05-15 | Module 7 Complete
Module 8: HTML Report & Audit | HTML Report & Audit APIs | Backend | M7 Done | 4 | Dev-2 (Lead) | 2026-05-06 | 2026-05-11
| Report UI & Export | UI | UX Draft | 4 | UI-1 | 2026-05-06 | 2026-05-11
| QA Scenario & Data Mapping | QA | Feature Draft | 3 | QA-1 | 2026-05-06 | 2026-05-08
| Integration & QA Execution | Backend/UI/QA | Integration | 4 | All | 2026-05-12 | 2026-05-17
| Bug Fixing & Retest | Backend/UI/QA | QA Defects | 3 | Dev-3 + QA-2 | 2026-05-18 | 2026-05-20 | Module 8 Complete
Module 9: Execution Dashboard | Execution Aggregation APIs | Backend | Module 8 Complete | 5 | Dev-1 (Lead) | 2026-05-15 | 2026-05-21
| Execution Dashboard UI | UI | UX Draft | 4 | UI-1 | 2026-05-18 | 2026-05-21
| QA Scenario & Metric Design | QA | Req + UX | 4 | QA-1 | 2026-05-18 | 2026-05-21
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 2 | Dev-1 + UI-1 | 2026-05-22 | 2026-05-25
| QA Dashboard Functional Execution | QA | Integration Complete | 4 | QA-1 | 2026-05-26 | 2026-05-30
| Bug Fixing (BE + UI) | Backend/UI | QA Defects | 2 | Dev-3 + UI-1 | 2026-06-02 | 2026-06-03
| QA Retest & Stabilization | QA | Fixes Done | 2 | QA-2 | 2026-06-04 | 2026-06-05 | Module 9 Complete
Module 10: Test Coverage Dashboard | Coverage Calculation APIs | Backend | Module 9 Partial | 5 | Dev-2 (Lead) | 2026-05-22 | 2026-05-28
| Coverage Dashboard UI | UI | UX Draft | 4 | UI-1 | 2026-05-26 | 2026-05-30
| QA Rule Mapping & Scenario Design | QA | Req + API Draft | 4 | QA-1 | 2026-05-26 | 2026-05-30
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 2 | Dev-2 + UI-1 | 2026-06-01 | 2026-06-02
| QA Coverage Accuracy Execution | QA | Integration Complete | 4 | QA-1 | 2026-06-03 | 2026-06-06
| Bug Fixing (BE + UI) | Backend/UI | QA Defects | 2 | Dev-3 + UI-1 | 2026-06-09 | 2026-06-10
| QA Retest & Coverage Stabilization | QA | Fixes Done | 2 | QA-2 | 2026-06-11 | 2026-06-12 | Module 10 Complete
Module 11: Health Check & Monitoring | Health Check API Design | Backend | Parallel | 3 | Dev-1 (Lead) | 2026-05-15 | 2026-05-19
| Service-Level Health APIs | Backend | Design Complete | 4 | Dev-1 (Lead) | 2026-05-20 | 2026-05-25
| Health Status UI | UI | UX Draft | 3 | UI-1 | 2026-05-20 | 2026-05-22
| QA Scenario & Failure Design | QA | Req + UX | 3 | QA-1 | 2026-05-20 | 2026-05-22
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 1 | Dev-1 + UI-1 | 2026-05-26 | 2026-05-26
| QA Health Check Execution | QA | Integration Complete | 3 | QA-1 | 2026-05-27 | 2026-05-29
| Bug Fixing & Retest | Backend/UI/QA | QA Defects | 2 | Dev-3 + QA-2 | 2026-06-01 | 2026-06-02 | Module 11 Complete
Module 12: User Management & Security | Auth Strategy & RBAC Design | Backend | Module 11 Done | 3 | Dev-2 (Lead) | 2026-06-02 | 2026-06-04
| Auth APIs & Middleware | Backend | Design Complete | 6 | Dev-2 (Lead) | 2026-06-05 | 2026-06-12
| User / Role / Login UI | UI | UX Draft | 4 | UI-1 | 2026-06-09 | 2026-06-12
| QA Scenario & Security Test Design | QA | Req + API Draft | 4 | QA-1 | 2026-06-09 | 2026-06-12
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 2 | Dev-2 + UI-1 | 2026-06-15 | 2026-06-16
| QA Functional & RBAC Execution | QA | Integration Complete | 3 | QA-1 | 2026-06-17 | 2026-06-19
| Bug Fixing & Retest | Backend/UI/QA | QA Defects | 2 | Dev-3 + QA-2 | 2026-06-19 | 2026-06-20 | Module 12 Complete
Module 13: Configuration Master Data | Master Data CRUD & RBAC APIs | Backend | Module 12 Partial | 4 | Dev-1 (Lead) | 2026-06-09 | 2026-06-12
| Configuration Screens UI | UI | UX Draft | 3 | UI-1 | 2026-06-11 | 2026-06-15
| QA Scenario & Data Rule Design | QA | Req + UX | 3 | QA-1 | 2026-06-11 | 2026-06-15
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 1 | Dev-1 + UI-1 | 2026-06-16 | 2026-06-16
| QA CRUD & RBAC Execution | QA | Integration Complete | 3 | QA-1 | 2026-06-17 | 2026-06-19
| Bug Fixing & Retest | Backend/UI/QA | QA Defects | 2 | Dev-3 + QA-2 | 2026-06-20 | 2026-06-21 | Module 13 Complete
All Modules | Pre-Regression Smoke | QA | All Features Complete | 1 | QA-2 | 2026-06-23 | 2026-06-23
| End-to-End Regression Testing | QA | Smoke Pass | 3 | QA-1 + QA-2 | 2026-06-24 | 2026-06-26
| E2E Bug Fixing (BE + UI) | Backend/UI | E2E Defects | 2 | Dev-3 + UI-1 | 2026-06-27 | 2026-06-28
| Final Retest & Sign-off | QA | Fixes Done | 1 | QA-2 | 2026-06-29 | 2026-06-29 | GO-LIVE

## Updated
Module | Task | Component | Dependency | Estimates (Days) | Resource | Start | End | Milestone
Module 1: API Connector | System Analysis & Solution Design | Backend | Project Start | 5 | Dev-1 (Lead) + Dev-3 | 2026-02-10 | 2026-02-16
| Connector Module Implementation | Backend | Analysis Complete | 5 | Dev-1 (Lead) + Dev-3 | 2026-02-17 | 2026-02-23
| Token Logic Implementation | Backend | Connector Impl | 5 | Dev-1 (Lead) + Dev-3 | 2026-02-24 | 2026-02-28
| API Connector UI | UI | UX Draft | 6 | UI-1 | 2026-02-18 | 2026-02-25
| QA Scenario & Test Case Design | QA | Req + UX | 4 | QA-1 | 2026-02-18 | 2026-02-23
| QA Test Data Preparation | QA | API Draft | 2 | QA-1 | 2026-02-24 | 2026-02-25
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 2 | Dev-1 + UI-1 + Dev-3 | 2026-03-02 | 2026-03-03
| QA Functional Execution | QA | Integration Complete | 4 | QA-1 | 2026-03-04 | 2026-03-09
| Bug Fixing & Optimization | Backend/UI | QA Defects | 2 | Dev-3 + UI-1 | 2026-03-10 | 2026-03-11
| QA Retest & Stabilization | QA | Fixes Done | 2 | QA-2 | 2026-03-12 | 2026-03-13 | Module 1 Complete
Module 2: DB Connector | System Analysis & Design | Backend | Parallel M1 | 5 | Dev-2 (Lead) + Dev-3 | 2026-02-10 | 2026-02-16
| DB Connector Backend & Pooling | Backend | Analysis | 5 | Dev-2 (Lead) + Dev-3 | 2026-02-17 | 2026-02-23
| Token Logic Implementation | Backend | Backend Impl | 5 | Dev-2 (Lead) + Dev-3 | 2026-02-24 | 2026-02-28
| DB Connector UI | UI | UX Draft | 6 | UI-1 | 2026-02-20 | 2026-02-27
| QA Scenario & Query Design | QA | Req + DB Model | 4 | QA-1 | 2026-02-18 | 2026-02-23
| QA Test Data & Validation Rules | QA | API Draft | 2 | QA-1 | 2026-02-24 | 2026-02-25
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 2 | Dev-2 + UI-1 + Dev-3 | 2026-03-02 | 2026-03-03
| QA Functional Execution | QA | Integration Complete | 4 | QA-1 | 2026-03-04 | 2026-03-09
| Bug Fixing & Optimization | Backend/UI | QA Defects | 2 | Dev-3 + UI-1 | 2026-03-10 | 2026-03-11
| QA Retest & Regression | QA | Fixes Done | 2 | QA-2 | 2026-03-12 | 2026-03-13 | Module 2 Complete
Module 3: Test Case Management | CRUD & Versioning APIs | Backend | M1 & M2 Complete | 7 | Dev-1 (Lead) + Dev-3 | 2026-03-18 | 2026-03-26
| Test Case Management UI | UI | UX Draft | 6 | UI-1 | 2026-03-23 | 2026-03-30
| QA Scenario & Coverage Design | QA | Feature Definition | 5 | QA-1 | 2026-03-18 | 2026-03-24
| QA Test Data & Versioning | QA | API Draft | 3 | QA-1 | 2026-03-25 | 2026-03-27
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 2 | Dev-1 + UI-1 + Dev-3 | 2026-03-31 | 2026-04-01
| QA Functional Execution | QA | Integration Complete | 4 | QA-1 | 2026-04-02 | 2026-04-07
| Bug Fixing & Optimization | Backend/UI | QA Defects | 2 | Dev-3 + UI-1 | 2026-04-08 | 2026-04-09
| QA Retest & Validation | QA | Fixes Done | 2 | QA-2 | 2026-04-10 | 2026-04-13 | Module 3 Complete
Module 4: Bulk Test Case Import | Import Template Design | Backend | M3 Complete | 5 | Dev-2 (Lead) + Dev-3 | 2026-04-14 | 2026-04-20
| Bulk Import Parser & Validation | Backend | Template Ready | 5 | Dev-2 (Lead) + Dev-3 | 2026-04-21 | 2026-04-27
| Bulk Import UI | UI | UX Draft | 5 | UI-1 | 2026-04-21 | 2026-04-27
| QA Scenario & Template Review | QA | Template Draft | 4 | QA-1 | 2026-04-21 | 2026-04-24
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 2 | Dev-2 + UI-1 + Dev-3 | 2026-04-28 | 2026-04-29
| QA Functional Execution | QA | Integration Complete | 4 | QA-1 | 2026-04-30 | 2026-05-05
| Bug Fixing & Optimization | Backend/UI | QA Defects | 2 | Dev-3 + UI-1 | 2026-05-06 | 2026-05-07
| QA Retest & Validation | QA | Fixes Done | 2 | QA-2 | 2026-05-08 | 2026-05-11 | Module 4 Complete
Module 5: Test Execution Engine | Execution Engine Core | Backend | M4 Complete | 5 | Dev-1 (Lead) + Dev-3 | 2026-04-15 | 2026-04-21
| Execution Trigger & Status UI | UI | UX Draft | 4 | UI-1 | 2026-04-16 | 2026-04-21
| QA Scenario & Flow Design | QA | Feature Draft | 4 | QA-1 | 2026-04-16 | 2026-04-21
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 2 | Dev-1 + UI-1 + Dev-3 | 2026-04-22 | 2026-04-23
| QA Execution Testing | QA | Integration Complete | 4 | QA-1 | 2026-04-24 | 2026-04-29
| Bug Fixing & Retest | Backend/UI/QA | QA Defects | 4 | Dev-3 + UI-1 + QA-2 | 2026-04-30 | 2026-05-05 | Module 5 Complete
Module 6: Validation Engine | Validation Rule Engine | Backend | M5 Complete | 5 | Dev-2 (Lead) + Dev-3 | 2026-04-22 | 2026-04-28
| QA Rule & Data Design | QA | Rule Draft | 4 | QA-1 | 2026-04-22 | 2026-04-25
| Integration & Unit Testing | Backend/UI | Backend Ready | 2 | Dev-2 + UI-1 + Dev-3 | 2026-04-29 | 2026-04-30
| QA Validation Execution | QA | Integration Complete | 3 | QA-1 | 2026-05-01 | 2026-05-05
| Bug Fixing & Retest | Backend/UI/QA | QA Defects | 4 | Dev-3 + UI-1 + QA-2 | 2026-05-06 | 2026-05-11 | Module 6 Complete
Module 7: Test Pack & Scheduling | Scheduler & Pack APIs | Backend | M6 Complete | 4 | Dev-1 (Lead) + Dev-3 | 2026-05-01 | 2026-05-06
| Test Pack & Scheduling UI | UI | UX Draft | 4 | UI-1 | 2026-05-01 | 2026-05-06
| QA Scenario & Execution | QA | Integration Ready | 5 | QA-1 | 2026-05-07 | 2026-05-13
| Bug Fixing & Retest | Backend/UI/QA | QA Defects | 2 | Dev-3 + QA-2 | 2026-05-14 | 2026-05-15 | Module 7 Complete
Module 8: HTML Report & Audit | HTML Report & Audit APIs | Backend | M7 Complete | 4 | Dev-2 (Lead) + Dev-3 | 2026-05-06 | 2026-05-11
| Report View UI & Export | UI | UX Draft | 4 | UI-1 | 2026-05-06 | 2026-05-11
| QA Scenario & Data Mapping | QA | Feature Draft | 3 | QA-1 | 2026-05-06 | 2026-05-08
| Integration & QA Execution | Backend/UI/QA | Integration Ready | 4 | All | 2026-05-12 | 2026-05-17
| Bug Fixing & Retest | Backend/UI/QA | QA Defects | 3 | Dev-3 + QA-2 | 2026-05-18 | 2026-05-20 | Module 8 Complete
Module 9: Execution Dashboard | Execution Aggregation APIs | Backend | Module 8 Complete | 5 | Dev-1 (Lead) + Dev-3 (Support) | 2026-05-15 | 2026-05-21
| Execution Dashboard UI | UI | UX Draft | 4 | UI-1 | 2026-05-18 | 2026-05-21
| QA Scenario & Metric Design | QA | Req + UX | 4 | QA-1 | 2026-05-18 | 2026-05-21
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 2 | Dev-1 + UI-1 + Dev-3 | 2026-05-22 | 2026-05-25
| QA Dashboard Functional Execution | QA | Integration Complete | 4 | QA-1 | 2026-05-26 | 2026-05-30
| Bug Fixing & Optimisation | Backend/UI | QA Defects | 2 | Dev-3 + UI-1 | 2026-06-02 | 2026-06-03
| QA Retest & Stabilization | QA | Fixes Done | 2 | QA-2 | 2026-06-04 | 2026-06-05 | Module 9 Complete
Module 10: Test Coverage Dashboard | Coverage Calculation APIs | Backend | Module 9 Partial | 5 | Dev-2 (Lead) + Dev-3 (Support) | 2026-05-22 | 2026-05-28
| Coverage Dashboard UI | UI | UX Draft | 4 | UI-1 | 2026-05-26 | 2026-05-30
| QA Rule Mapping & Scenario Design | QA | Req + API Draft | 4 | QA-1 | 2026-05-26 | 2026-05-30
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 2 | Dev-2 + UI-1 + Dev-3 | 2026-06-01 | 2026-06-02
| QA Coverage Accuracy Execution | QA | Integration Complete | 4 | QA-1 | 2026-06-03 | 2026-06-06
| Bug Fixing & Optimization | Backend/UI | QA Defects | 2 | Dev-3 + UI-1 | 2026-06-09 | 2026-06-10
| QA Retest & Stabilization | QA | Fixes Done | 2 | QA-2 | 2026-06-11 | 2026-06-12 | Module 10 Complete
Module 11: Health Check & Monitoring | Health Check API Design | Backend | Parallel | 3 | Dev-1 (Lead) + Dev-3 (Support) | 2026-05-15 | 2026-05-19
| Service-Level Health APIs | Backend | Design Complete | 4 | Dev-1 + Dev-3 | 2026-05-20 | 2026-05-25
| Health Status UI | UI | UX Draft | 3 | UI-1 | 2026-05-20 | 2026-05-22
| QA Scenario & Failure Design | QA | Req + UX | 3 | QA-1 | 2026-05-20 | 2026-05-22
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 1 | Dev-1 + UI-1 + Dev-3 | 2026-05-26 | 2026-05-26
| QA Health Check Execution | QA | Integration Complete | 3 | QA-1 | 2026-05-27 | 2026-05-29
| Bug Fixing & Retest | Backend/UI/QA | QA Defects | 2 | Dev-3 + QA-2 | 2026-06-01 | 2026-06-02 | Module 11 Complete
Module 12: User Management & Security | Auth Strategy & RBAC Design | Backend | Module 11 Done | 3 | Dev-2 (Lead) + Dev-3 (Support) | 2026-06-02 | 2026-06-04
| Auth APIs & Middleware | Backend | Design Complete | 6 | Dev-2 + Dev-3 | 2026-06-05 | 2026-06-12
| User / Role / Login UI | UI | UX Draft | 4 | UI-1 | 2026-06-09 | 2026-06-12
| QA Scenario & Security Design | QA | Req + API Draft | 4 | QA-1 | 2026-06-09 | 2026-06-12
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 2 | Dev-2 + UI-1 + Dev-3 | 2026-06-15 | 2026-06-16
| QA Functional & RBAC Execution | QA | Integration Complete | 3 | QA-1 | 2026-06-17 | 2026-06-19
| Bug Fixing & Retest | Backend/UI/QA | QA Defects | 2 | Dev-3 + QA-2 | 2026-06-19 | 2026-06-20 | Module 12 Complete
Module 13: Configuration Master Data | Master Data CRUD & RBAC APIs | Backend | Module 12 Partial | 4 | Dev-1 (Lead) + Dev-3 (Support) | 2026-06-09 | 2026-06-12
| Configuration Screens UI | UI | UX Draft | 3 | UI-1 | 2026-06-11 | 2026-06-15
| QA Scenario & Data Rule Design | QA | Req + UX | 3 | QA-1 | 2026-06-11 | 2026-06-15
| Integration & Unit Testing | Backend/UI | Backend + UI Ready | 1 | Dev-1 + UI-1 + Dev-3 | 2026-06-16 | 2026-06-16
| QA CRUD & RBAC Execution | QA | Integration Complete | 3 | QA-1 | 2026-06-17 | 2026-06-19
| Bug Fixing & Retest | Backend/UI/QA | QA Defects | 2 | Dev-3 + QA-2 | 2026-06-20 | 2026-06-21 | Module 13 Complete
All Modules | Pre-Regression Smoke | QA | All Features Complete | 1 | QA-2 | 2026-06-23 | 2026-06-23
| End-to-End Regression Testing | QA | Smoke Pass | 3 | QA-1 + QA-2 | 2026-06-24 | 2026-06-26
| E2E Bug Fixing (BE + UI) | Backend/UI | E2E Defects | 2 | Dev-3 + UI-1 | 2026-06-27 | 2026-06-28
| Final Retest & Sign-off | QA | Fixes Done | 1 | QA-2 | 2026-06-29 | 2026-06-29 | GO-LIVE

## Holidays
Holiday Date
26-Jan-2026
04-Mar-2026
01-May-2026