## Module 1 - API Connector
Module | Task | SubTask | Outcome | Component | Dependency | Elapsed Days | Resource | Planned Start Date | Planned End Date
Module 1: API Connector | System Analysis & Solution Design | Understand the requirement | Clear understanding of payment & validation flow | Backend | Project Start | 1 | QA + Dev-1 (Lead) | 10-Feb-2026
Module 1: API Connector | System Analysis & Solution Design | Analyze API types & patterns | Supported API types identified | Backend | Project Start | 1 | QA + Dev-1 (Lead) | 11-Feb-2026
Module 1: API Connector | System Analysis & Solution Design | Auth mechanism analysis | OAuth2 / Bearer / Basic finalized | Backend | Project Start | 1 | QA + Dev-1 (Lead) | 12-Feb-2026
Module 1: API Connector | System Analysis & Solution Design | Define connector architecture | High-level design prepared | Backend | Project Start | 2 | QA + Dev-1 (Lead) | 13-Feb-2026
Module 1: API Connector | Connector Module Implementation | Base connector implementation | Reusable API execution layer | Backend | Analysis Complete | 2 | Dev-1 (Lead) + Dev-3 | 17-Feb-2026
Module 1: API Connector | Connector Module Implementation | HTTP methods support | GET/POST/PUT/DELETE supported | Backend | Analysis Complete | 1 | Dev-1 (Lead) + Dev-3 | 19-Feb-2026
Module 1: API Connector | Connector Module Implementation | Header & parameter handling | Dynamic request support | Backend | Analysis Complete | 1 | Dev-1 (Lead) + Dev-3 | 20-Feb-2026
Module 1: API Connector | Connector Module Implementation | Timeout & retry handling | Configurable retry & timeout | Backend | Analysis Complete | 1 | Dev-1 (Lead) + Dev-3 | 21-Feb-2026
Module 1: API Connector | Token Logic Implementation | Basic & API key auth | Multiple auth types supported | Backend | Connector Impl | 1 | Dev-1 (Lead) + Dev-3 | 24-Feb-2026
Module 1: API Connector | Token Logic Implementation | Token generation logic | Token-based auth working | Backend | Connector Impl | 2 | Dev-1 (Lead) + Dev-3 | 25-Feb-2026
Module 1: API Connector | Token Logic Implementation | Token refresh & reuse | Stable executions | Backend | Connector Impl | 2 | Dev-1 (Lead) + Dev-3 | 27-Feb-2026
Module 1: API Connector | API Connector UI | Connector listing UI | Search & filter enabled | UI | UX Draft | 1 | UI-1 | 18-Feb-2026
Module 1: API Connector | API Connector UI | Create/Edit connector UI | Payment & validation UI ready | UI | UX Draft | 2 | UI-1 | 19-Feb-2026
Module 1: API Connector | API Connector UI | Auth configuration UI | Dynamic auth UI per type | UI | UX Draft | 1 | UI-1 | 21-Feb-2026
Module 1: API Connector | API Connector UI | Header & response UI | Header & extraction UI | UI | UX Draft | 2 | UI-1 | 22-Feb-2026
Module 1: API Connector | QA Scenario & Test Case Design | Define test scenarios | Test coverage prepared | QA | Req + UX | 2 | QA-1 | 18-Feb-2026
Module 1: API Connector | QA Scenario & Test Case Design | Review & finalize cases | QA sign-off | QA | Req + UX | 2 | QA-1 | 20-Feb-2026
Module 1: API Connector | QA Test Data Preparation | Prepare input payloads | Payment files ready | QA | API Draft | 1 | QA-1 | 24-Feb-2026
Module 1: API Connector | QA Test Data Preparation | Prepare expected payloads | Validation data ready | QA | API Draft | 1 | QA-1 | 25-Feb-2026
Module 1: API Connector | Integration & Unit Testing | Unit testing | Unit test completed | Backend/UI | Backend + UI Ready | 2 | Dev-1 + UI-1 | 3-Mar-2026
Module 1: API Connector | Integration & Unit Testing | Integration testing | End-to-end verified | Backend/UI | Backend + UI Ready | 2 | Dev-1 + UI-1 | 5-Mar-2026
Module 1: API Connector | QA Functional Execution | Test execution | Execution completed | QA | Integration Complete | 4 | QA-1 | 4-Mar-2026
Module 1: API Connector | Bug Fixing & Optimization | Fix defects | All defects resolved | Backend/UI | QA Defects | 2 | Dev-3 + UI-1 | 10-Mar-2026
Module 1: API Connector | QA Retest & Stabilization | Retest | Stable build | QA | Fixes Done | 1 | QA-2 | 12-Mar-2026
Module 1: API Connector | QA Retest & Stabilization | Final sign-off | Module approved | QA | Retest | 1 | QA-2 | 13-Mar-2026
Module 1: API Connector | System Analysis & Solution Design | Understand requirements & payment flows | Clear understanding of end-to-end API flow | Backend | Project Start | 2 | QA + Dev-1 (Lead)
Module 1: API Connector | System Analysis & Solution Design | Analyze API types & auth mechanisms | Supported API & auth types identified | Backend | Requirement Understanding | 2 | Dev-1
Module 1: API Connector | Connector Module Implementation | Base API connector framework | Reusable API execution layer | Backend | Design Complete | 3 | Dev-1 + Dev-2
Module 1: API Connector | Connector Module Implementation | HTTP methods support | GET/POST/PUT/DELETE supported | Backend | Base Framework Ready | 2 | Dev-2
Module 1: API Connector | Token Logic Implementation | OAuth2 / Bearer / Basic auth | Multiple auth types working | Backend | Connector Impl | 3 | Dev-1 (Lead)
Module 1: API Connector | Token Logic Implementation | Token extraction & reuse | Stable token executions | Backend | Auth Logic Ready | 2 | Dev-1
Module 1: API Connector | API Connector UI | Connector screens | Usable API Connector UI | UI | Backend APIs Ready | 4 | UI-1
Module 1: API Connector | QA Scenario & Test Case Design | Design scenarios | Full coverage test cases | QA | UI Draft | 2 | QA-1
Module 1: API Connector | Integration & Unit Testing | End-to-end testing | Integrated stable module | Backend/UI | Dev Complete | 3 | Dev-1 + QA-1
Module 1: API Connector | QA Functional Execution | Execute test cases | Defects logged | QA | Integration Done | 2 | QA-1
Module 1: API Connector | Bug Fixing & Optimization | Fix & optimize | Defect-free module | Backend/UI | QA Defects | 2 | Dev-1 + UI-1
Module 1: API Connector | QA Retest & Stabilization | Regression testing | Release-ready module | QA | Fixes Done | 2 | QA-2

## Sheet1
Module | Task | SubTask | Outcome | Component | Dependency | Elapsed Days | Resource | Planned Start Date | Planned End Date
Module 1: API Connector | System Analysis & Solution Design | Understand the requirement | Clear understanding of payment & validation flow | Backend | Project Start | 1 | QA + Dev-1 | 2026-02-10 | 2026-02-10
|  | Analyze API types & patterns | Supported API types identified | Backend | Project Start | 1 | QA + Dev-1 | 2026-02-11 | 2026-02-11
|  | Auth mechanism analysis | OAuth2 / Bearer / Basic finalized | Backend | Project Start | 1 | QA + Dev-1 | 2026-02-12 | 2026-02-12
|  | Define connector architecture | High-level connector design prepared | Backend | Project Start | 2 | QA + Dev-1 | 2026-02-13 | 2026-02-16
| Connector Module Implementation | Base connector implementation | Reusable API execution layer | Backend | Analysis Complete | 2 | Dev-1 | 2026-02-17 | 2026-02-18
|  | HTTP methods support | GET / POST / PUT / DELETE supported | Backend | Analysis Complete | 1 | Dev-1 | 2026-02-19 | 2026-02-19
|  | Header & parameter handling | Dynamic headers & params support | Backend | Analysis Complete | 1 | Dev-1 | 2026-02-20 | 2026-02-20
|  | Timeout & retry handling | Configurable retry & timeout logic | Backend | Analysis Complete | 1 | Dev-1 | 2026-02-21 | 2026-02-21
| Token Logic Implementation | Basic & API key auth | Static auth mechanisms supported | Backend | Connector Impl | 1 | Dev-1 | 2026-02-24 | 2026-02-24
|  | Token generation logic | Token-based auth working | Backend | Connector Impl | 2 | Dev-1 | 2026-02-25 | 2026-02-26
|  | Token refresh & reuse | Stable token lifecycle handling | Backend | Connector Impl | 2 | Dev-1 | 2026-02-27 | 2026-03-02
| API Connector UI | Connector listing UI | Search & filter enabled | UI | UX Draft | 1 | UI-1 | 2026-02-18 | 2026-02-18
|  | Create/Edit connector UI | Payment & validation UI ready | UI | UX Draft | 2 | UI-1 | 2026-02-19 | 2026-02-20
|  | Auth configuration UI | Dynamic auth UI per type | UI | UX Draft | 1 | UI-1 | 2026-02-21 | 2026-02-21
|  | Header & response UI | Header & response extraction UI | UI | UX Draft | 2 | UI-1 | 2026-02-22 | 2026-02-23
| QA Scenario & Test Case Design | Define test scenarios | Test coverage prepared | QA | Req + UX | 2 | QA-1 | 2026-02-18 | 2026-02-19
|  | Review & finalize cases | QA sign-off completed | QA | Req + UX | 2 | QA-1 | 2026-02-20 | 2026-02-23
| QA Test Data Preparation | Prepare input payloads | Payment input files ready | QA | API Draft | 1 | QA-1 | 2026-02-24 | 2026-02-24
|  | Prepare expected payloads | Validation payloads ready | QA | API Draft | 1 | QA-1 | 2026-02-25 | 2026-02-25
| Integration & Unit Testing | Unit testing | Unit tests completed | Backend/UI | Backend + UI Ready | 2 | Dev-1 + UI-1 | 2026-03-03 | 2026-03-04
|  | Integration testing | End-to-end flow verified | Backend/UI | Backend + UI Ready | 2 | Dev-1 + UI-1 | 2026-03-05 | 2026-03-06
| QA Functional Execution | Test execution | Test execution completed | QA | Integration Complete | 4 | QA-1 | 2026-03-04 | 2026-03-09
| Bug Fixing & Optimization | Fix defects | All defects resolved | Backend/UI | QA Defects | 2 | Dev-1 + UI-1 | 2026-03-10 | 2026-03-11
| QA Retest & Stabilization | Retest | Stable build validated | QA | Fixes Done | 1 | QA-2 | 2026-03-12 | 2026-03-12
|  | Final sign-off | Module approved | QA | Retest | 1 | QA-2 | 2026-03-13 | 2026-03-13
Module 2: DB Connector | System Analysis & Solution Design | Understand DB validation requirements | Clear understanding of DB validation needs | Backend | Project Start | 1 | QA + Dev-2
|  | Analyze supported DB types | Supported DB engines identified | Backend | Project Start | 1 | QA + Dev-2
|  | Analyze query & join patterns | Query patterns finalized | Backend | Project Start | 1 | QA + Dev-2
|  | Define DB connector architecture | DB connector design prepared | Backend | Project Start | 2 | QA + Dev-2
| DB Connector Backend & Pooling | Design DB connection pooling strategy | Connection pooling approach finalized | Backend | Analysis Complete | 1 | Dev-2
|  | Implement DB connection manager | DB connections managed centrally | Backend | Analysis Complete | 2 | Dev-2
|  | Multi-environment DB configuration | Env-based DB configs supported | Backend | Analysis Complete | 1 | Dev-2
|  | Connection timeout & retry handling | Stable DB retries & timeouts | Backend | Analysis Complete | 1 | Dev-2
| Token Logic Implementation | Runtime variable binding in queries | Runtime values injected in SQL | Backend | Connector Impl | 1 | Dev-2
|  | Token / runtime value reuse | Shared runtime data reuse | Backend | Connector Impl | 1 | Dev-2
|  | Secure credential handling | Secure DB credential handling | Backend | Connector Impl | 1 | Dev-2
| DB Connector Core Implementation | SELECT query execution | SELECT queries executed | Backend | Core Ready | 1 | Dev-2
|  | Multiple query (0..N) execution | Multiple queries supported | Backend | Core Ready | 1 | Dev-2
|  | Result-set parsing | DB result sets parsed | Backend | Core Ready | 1 | Dev-2
|  | DB column extraction & mapping | DB fields mapped | Backend | Core Ready | 1 | Dev-2
|  | Expected vs actual DB validation | DB validation working | Backend | Core Ready | 1 | Dev-2
| DB Connector UI | Connector listing UI | DB connector listing UI ready | UI | UX Draft | 1 | UI-1
|  | Create/Edit DB connector UI | DB connector configuration UI | UI | UX Draft | 2 | UI-1
|  | DB connection configuration UI | DB config UI ready | UI | UX Draft | 1 | UI-1
|  | Query editor UI | SQL query editor available | UI | UX Draft | 1 | UI-1
|  | Response mapping & validation UI | DB response mapping UI | UI | UX Draft | 1 | UI-1
| QA Scenario & Query Design | Define DB validation scenarios | DB scenarios designed | QA | Req + UX | 2 | QA-2
|  | Review & finalize DB scenarios | DB test cases finalized | QA | Req + UX | 1 | QA-2
| QA Test Data Preparation | Prepare DB test data | DB test data ready | QA | DB Draft | 1 | QA-2
|  | Prepare expected DB outputs | Expected DB outputs ready | QA | DB Draft | 1 | QA-2
| Integration & Unit Testing | DB unit testing | DB unit tests passed | Backend/UI | Backend Ready | 2 | Dev-2 + QA-2
|  | API + DB integration testing | API & DB validated together | Backend/UI | API Ready | 2 | Dev-2 + QA-2
|  | End-to-end validation testing | Complete validation flow verified | Backend/UI | Integration Ready | 2 | Dev-2 + QA-2
| QA Functional Execution | Execute DB validation test cases | DB test execution completed | QA | Integration Complete | 2 | QA-2
|  | Parallel API + DB execution | Parallel validation verified | QA | Integration Complete | 1 | QA-2
| Bug Fixing & Optimization | Fix DB defects | DB defects resolved | Backend/UI | QA Defects | 2 | Dev-2 + UI-1
|  | Query optimization & performance tuning | Optimized DB queries | Backend | QA Defects | 1 | Dev-2
| QA Retest & Stabilization | Retest DB scenarios | DB retest successful | QA | Fixes Done | 1 | QA-2
|  | Regression testing | DB regression passed | QA | Fixes Done | 1 | QA-2
|  | Final sign-off | Module approved | QA | Retest | 1 | QA-2