## Module_Wise_3_Columns
Module | Task | Resource | Planned Start Date
Module 1: API Connector | System Analysis & Solution Design | Dev-1 (Lead) + Dev-3 (Support) | 10-Feb-2026
Module 1: API Connector | Connector Module Implementation | Dev-1 (Lead) + Dev-3 (Support) | 13-Feb-2026
Module 1: API Connector | Token Logic Implementation | Dev-2 (Lead) + Dev-3 (Support) | 17-Feb-2026
Module 1: API Connector | API Connector UI | UI-1 | 13-Feb-2026
Module 1: API Connector | QA Scenario & Data Preparation | QA-1 | 14-Feb-2026
Module 1: API Connector | QA Functional & Integration Testing | QA-1 | 20-Feb-2026
Module 1: API Connector | Backend Bug Fixing | Dev-3 | 28-Feb-2026
Module 1: API Connector | UI Bug Fixing | UI-1 | 28-Feb-2026
Module 1: API Connector | QA Bug Retest & Stabilization | QA-2 | 02-Mar-2026
Module 2: DB Connector | System Analysis & Solution Design | Dev-2 (Lead) + Dev-3 (Support) | 10-Feb-2026
Module 2: DB Connector | DB Connector Backend & Pooling | Dev-2 (Lead) + Dev-3 (Support) | 13-Feb-2026
Module 2: DB Connector | Token Logic Implementation | Dev-1 (Lead) + Dev-3 (Support) | 17-Feb-2026
Module 2: DB Connector | DB Connector UI | UI-1 | 20-Feb-2026
Module 2: DB Connector | QA Test Case Design & Query Validation | QA-1 | 21-Feb-2026
Module 2: DB Connector | QA Functional & Data Accuracy Testing | QA-1 | 27-Feb-2026
Module 2: DB Connector | Backend Bug Fixing | Dev-3 | 05-Mar-2026
Module 2: DB Connector | UI Bug Fixing | UI-1 | 05-Mar-2026
Module 2: DB Connector | QA Bug Retest & Regression | QA-2 | 06-Mar-2026
Module 3: Test Case Management | Test Case CRUD & Versioning APIs | Dev-1 (Lead) + Dev-3 (Support) | 24-Feb-2026
Module 3: Test Case Management | Test Case Management UI | UI-1 | 26-Feb-2026
Module 3: Test Case Management | QA Test Case Design & Rule Matrix | QA-1 | 05-Mar-2026
Module 3: Test Case Management | QA Functional & UI Validation | QA-1 | 10-Mar-2026
Module 3: Test Case Management | Backend Bug Fixing | Dev-3 | 18-Mar-2026
Module 3: Test Case Management | UI Bug Fixing | UI-1 | 18-Mar-2026
Module 3: Test Case Management | QA Bug Retest & Version Validation | QA-2 | 20-Mar-2026
Module 4: Bulk Test Case Import | Import Template Design | Dev-1 (Lead) + Dev-3 (Support) | 23-Mar-2026
Module 4: Bulk Test Case Import | Bulk Import Parser & Validation | Dev-2 (Lead) + Dev-3 (Support) | 26-Mar-2026
Module 4: Bulk Test Case Import | Bulk Import UI | UI-1 | 26-Mar-2026
Module 4: Bulk Test Case Import | QA Template Review & Data Prep | QA-1 | 01-Apr-2026
Module 4: Bulk Test Case Import | QA Bulk Import Functional Testing | QA-1 | 07-Apr-2026
Module 4: Bulk Test Case Import | Backend Bug Fixing | Dev-3 | 13-Apr-2026
Module 4: Bulk Test Case Import | UI Bug Fixing | UI-1 | 13-Apr-2026
Module 4: Bulk Test Case Import | QA Bug Retest & Partial Success Validation | QA-2 | 16-Apr-2026
Module 5: Test Execution Engine | Execution Engine Core Services | Dev-1 (Lead) + Dev-3 (Support) | 18-Apr-2026
Module 5: Test Execution Engine | Execution Trigger & Status UI | UI-1 | 22-Apr-2026
Module 5: Test Execution Engine | QA Scenario Design (Execution Flow) | QA-1 | 24-Apr-2026
Module 5: Test Execution Engine | QA Execution & Parallel Run Testing | QA-1 | 30-Apr-2026
Module 5: Test Execution Engine | Backend Bug Fixing | Dev-3 | 04-May-2026
Module 5: Test Execution Engine | UI Bug Fixing | UI-1 | 04-May-2026
Module 5: Test Execution Engine | QA Bug Retest & Stability Validation | QA-2 | 06-May-2026
Module 6: Validation Engine | Validation Rule Engine & DB Compare | Dev-2 (Lead) + Dev-3 (Support) | 06-May-2026
Module 6: Validation Engine | QA Rule Coverage & Expected Data Prep | QA-1 | 09-May-2026
Module 6: Validation Engine | QA Validation Accuracy Testing | QA-1 | 13-May-2026
Module 6: Validation Engine | Backend Bug Fixing | Dev-3 | 16-May-2026
Module 6: Validation Engine | UI Bug Fixing | UI-1 | 16-May-2026
Module 6: Validation Engine | QA Bug Retest & Rule Stabilization | QA-2 | 18-May-2026
Module 7: Test Pack & Scheduling | Scheduler & Pack Mapping APIs | Dev-2 (Lead) + Dev-3 (Support) | 22-Apr-2026
Module 7: Test Pack & Scheduling | Test Pack UI & Scheduling | UI-1 | 25-Apr-2026
Module 7: Test Pack & Scheduling | QA Scheduling Scenario Design | QA-1 | 30-Apr-2026
Module 7: Test Pack & Scheduling | QA Schedule Execution Testing | QA-1 | 05-May-2026
Module 7: Test Pack & Scheduling | Backend Bug Fixing | Dev-3 | 09-May-2026
Module 7: Test Pack & Scheduling | UI Bug Fixing | UI-1 | 09-May-2026
Module 7: Test Pack & Scheduling | QA Bug Retest & Retry Validation | QA-2 | 13-May-2026
Module 8: HTML Report & Audit | HTML Report & Audit APIs | Dev-1 (Lead) + Dev-3 (Support) | 28-Apr-2026
Module 8: HTML Report & Audit | Report View UI & Export | UI-1 | 30-Apr-2026
Module 8: HTML Report & Audit | QA Report Structure & Data Mapping | QA-1 | 05-May-2026
Module 8: HTML Report & Audit | QA Report Functional & Export Testing | QA-1 | 08-May-2026
Module 8: HTML Report & Audit | Backend Bug Fixing | Dev-3 | 11-May-2026
Module 8: HTML Report & Audit | UI Bug Fixing | UI-1 | 11-May-2026
Module 8: HTML Report & Audit | QA Bug Retest & Audit Validation | QA-2 | 14-May-2026
Module 9: Execution Dashboard | Execution Aggregation APIs | Dev-1 (Lead) + Dev-3 (Support) | 15-May-2026
Module 9: Execution Dashboard | Execution Dashboard UI | UI-1 | 18-May-2026
Module 9: Execution Dashboard | QA Dashboard Metric Validation | QA-1 | 22-May-2026
Module 9: Execution Dashboard | QA Dashboard UI & Data Testing | QA-1 | 26-May-2026
Module 9: Execution Dashboard | Backend Bug Fixing | Dev-3 | 27-May-2026
Module 9: Execution Dashboard | UI Bug Fixing | UI-1 | 27-May-2026
Module 9: Execution Dashboard | QA Bug Retest & Trend Validation | QA-2 | 29-May-2026
Module 10: Test Coverage Dashboard | Coverage Calculation APIs | Dev-2 (Lead) + Dev-3 (Support) | 20-May-2026
Module 10: Test Coverage Dashboard | Coverage Dashboard UI | UI-1 | 23-May-2026
Module 10: Test Coverage Dashboard | QA Coverage Rule Mapping Review | QA-1 | 28-May-2026
Module 10: Test Coverage Dashboard | QA Coverage Accuracy Testing | QA-1 | 01-Jun-2026
Module 10: Test Coverage Dashboard | Backend Bug Fixing | Dev-3 | 03-Jun-2026
Module 10: Test Coverage Dashboard | UI Bug Fixing | UI-1 | 03-Jun-2026
Module 10: Test Coverage Dashboard | QA Bug Retest & Coverage Stabilization | QA-2 | 05-Jun-2026
Module 11: Health Check & Monitoring | Health Check API Design | Dev-1 (Lead) + Dev-3 (Support) | 22-May-2026
Module 11: Health Check & Monitoring | Service-Level Health APIs | Dev-2 (Lead) + Dev-3 (Support) | 26-May-2026
Module 11: Health Check & Monitoring | Health Status UI | UI-1 | 29-May-2026
Module 11: Health Check & Monitoring | QA Health Scenario Design | QA-1 | 02-Jun-2026
Module 11: Health Check & Monitoring | QA Health Check Validation | QA-2 | 04-Jun-2026
Module 12: User Management & Security | Auth Strategy & RBAC Design | Dev-1 | 27-May-2026
Module 12: User Management & Security | Auth APIs & Middleware | Dev-1 (Lead) + Dev-3 (Support) | 30-May-2026
Module 12: User Management & Security | User / Role / Login UI | UI-1 | 02-Jun-2026
Module 12: User Management & Security | QA Scenario & Test Case Design | QA-1 | 06-Jun-2026
Module 12: User Management & Security | QA Functional Testing | QA-1 | 10-Jun-2026
Module 12: User Management & Security | Backend Bug Fixing | Dev-3 | 15-Jun-2026
Module 12: User Management & Security | UI Bug Fixing | UI-1 | 15-Jun-2026
Module 12: User Management & Security | QA Bug Retest & Regression | QA-2 | 17-Jun-2026
Module 13: Configuration Master Data | Master Data CRUD & RBAC APIs | Dev-2 (Lead) + Dev-3 (Support) | 02-Jun-2026
Module 13: Configuration Master Data | Configuration Screens UI | UI-1 | 06-Jun-2026
Module 13: Configuration Master Data | QA Master Data Scenario Design | QA-1 | 11-Jun-2026
Module 13: Configuration Master Data | QA CRUD & RBAC Validation | QA-1 | 13-Jun-2026
Module 13: Configuration Master Data | Backend Bug Fixing | Dev-3 | 17-Jun-2026
Module 13: Configuration Master Data | UI Bug Fixing | UI-1 | 17-Jun-2026
Module 13: Configuration Master Data | QA Bug Retest & Regression | QA-2 | 19-Jun-2026
All Modules | Pre-Regression Smoke Test | QA-2 | 21-Jun-2026
All Modules | End-to-End Regression & Go-Live | QA-1 + QA-2 | 23-Jun-2026