## Module 1 - API Connector (Descriptive)
Module | Task | SubTask (Client Friendly Description) | Outcome | Component | Dependency
Module 1: API Connector | System Analysis & Solution Design | Understand business requirements, payment flows, and validation needs for API connectors | Clear understanding of payment & validation flow with connectors | Backend | Project Start
Module 1: API Connector | System Analysis & Solution Design | Analyze different API styles, request/response formats, and integration patterns | Supported API types and patterns identified | Backend | Project Start
Module 1: API Connector | System Analysis & Solution Design | Analyze and finalize authentication approaches such as OAuth2, Bearer, Basic, API Key | Authentication mechanisms finalized | Backend | Project Start
Module 1: API Connector | System Analysis & Solution Design | Define overall connector architecture including execution flow and extensibility | High-level connector architecture prepared | Backend | Project Start
Module 1: API Connector | Connector Module Implementation | Develop reusable base framework to execute APIs in a standardized manner | Reusable API execution layer implemented | Backend | Analysis Complete
Module 1: API Connector | Connector Module Implementation | Add support for HTTP methods like GET, POST, PUT, DELETE | All standard HTTP methods supported | Backend | Analysis Complete
Module 1: API Connector | Connector Module Implementation | Implement dynamic handling of headers, query parameters, and request payloads | Dynamic headers, parameters, and body support enabled | Backend | Analysis Complete
Module 1: API Connector | Connector Module Implementation | Implement configurable timeout settings and retry logic | Retry and timeout logic configurable | Backend | Analysis Complete
Module 1: API Connector | Token Logic Implementation | Implement static authentication mechanisms like API Key and Basic Auth | Static authentication mechanisms supported | Backend | Connector Impl
Module 1: API Connector | Token Logic Implementation | Implement token generation flow using authentication APIs | Token-based authentication working | Backend | Connector Impl
Module 1: API Connector | Token Logic Implementation | Implement token refresh, caching, and reuse across executions | Stable token lifecycle handling implemented | Backend | Connector Impl
Module 1: API Connector | API Connector UI | Design UI to list connectors with search and filter options | Connector listing UI available | UI | UX Draft
Module 1: API Connector | API Connector UI | Develop UI screens to create and edit connector configurations | Create/Edit connector UI ready | UI | UX Draft
Module 1: API Connector | API Connector UI | Develop UI for dynamic authentication configuration per connector | Authentication configuration UI ready | UI | UX Draft
Module 1: API Connector | API Connector UI | Develop UI to configure headers and extract response fields | Header and response extraction UI ready | UI | UX Draft
Module 1: API Connector | QA Scenario & Test Case Design | Identify functional, negative, and edge case scenarios for API connectors | Comprehensive test coverage prepared | QA | Req + UX
Module 1: API Connector | QA Scenario & Test Case Design | Review, validate, and finalize test cases with stakeholders | QA sign-off completed | QA | Req + UX
Module 1: API Connector | QA Test Data Preparation | Prepare input request payloads for testing | Input test data ready | QA | API Draft
Module 1: API Connector | QA Test Data Preparation | Prepare expected response payloads for validation | Expected validation data ready | QA | API Draft
Module 1: API Connector | Integration & Unit Testing | Backend developer performs unit testing of API logic and error handling | Backend unit tests completed | Backend | Backend Ready
Module 1: API Connector | Integration & Unit Testing | UI developer performs unit testing of connector UI screens | UI unit tests completed | UI | UI Ready
Module 1: API Connector | Integration & Unit Testing | Verify end-to-end connector execution across backend and UI | Integrated end-to-end flow verified | Backend/UI | Backend + UI Ready
Module 1: API Connector | QA Functional Execution | Execute functional test cases on integrated build | Functional test execution completed | QA | Integration Complete
Module 1: API Connector | Bug Fixing & Feedback Implementation | Backend developer fixes defects and incorporates feedback | Backend defects resolved | Backend | QA Defects
Module 1: API Connector | Bug Fixing & Feedback Implementation | UI developer fixes UI defects and incorporates feedback | UI defects resolved | UI | QA Defects
Module 1: API Connector | QA Retest & Stabilization | QA retests fixes and validates system stability | Stable build validated | QA | Fixes Done
Module 1: API Connector | QA Retest & Stabilization | Final QA sign-off for module release | Module approved for release | QA | Retest