## Phase 2
Module | Task | Subtask | Component | Estimates (Days) | Resource | Planned Start Date | Planned End Date
Module 1: User Management & Security | Requirement Analysis | Auth, RBAC & audit requirements | Backend | 2 | Backend Dev
| Requirement Analysis | Login/User/Role UI flow analysis | UI | 2 | UI Dev
| Requirement Analysis | Auth & RBAC test scenario prep | QA | 2 | QA
| Design | JWT/OAuth/SSO design | Backend | 3 | Backend Dev
| Design | User/Role DB schema | Backend | 2 | Backend Dev
| Design | UI wireframes & validations | UI | 3 | UI Dev
| Backend Development | Login API | Backend | 3 | Backend Dev
| Backend Development | Logout API | Backend | 2 | Backend Dev
| Backend Development | Token generation & refresh | Backend | 4 | Backend Dev
| Backend Development | User CRUD APIs | Backend | 4 | Backend Dev
| Backend Development | Role & permission mapping | Backend | 4 | Backend Dev
| Backend Development | Authorization middleware | Backend | 4 | Backend Dev
| Backend Development | Audit logging & hardening | Backend | 3 | Backend Dev
| UI Development | Login screen | UI | 3 | UI Dev
| UI Development | User management screens | UI | 5 | UI Dev
| UI Development | Role & permission screens | UI | 4 | UI Dev
| UI Development | UI validations & errors | UI | 3 | UI Dev
| QA Test Design | Auth & role test cases | QA | 4 | QA
| QA Execution | Functional & security execution | QA | 5 | QA
| QA Execution | Regression testing | QA | 3 | QA
Module 2: API Connector Master | Requirement Analysis | Connector & env requirement analysis | Backend | 2 | Backend Dev
| Design | Connector schema & encryption | Backend | 3 | Backend Dev
| Design | Connector UI forms | UI | 3 | UI Dev
| Backend Development | Connector CRUD APIs | Backend | 5 | Backend Dev
| Backend Development | Token generation per connector | Backend | 4 | Backend Dev
| Backend Development | Token caching & expiry | Backend | 3 | Backend Dev
| Backend Development | Health check API | Backend | 3 | Backend Dev
| UI Development | Connector create/update UI | UI | 5 | UI Dev
| UI Development | Auth type & header config UI | UI | 4 | UI Dev
| UI Development | Environment handling | UI | 3 | UI Dev
| QA Test Design | Token & auth test cases | QA | 3 | QA
| QA Execution | Env, retry & failure validation | QA | 5 | QA
Module 3: DB Connector Master | Design | DB connector & key mapping design | Backend | 2 | Backend Dev
| Backend Development | Secure DB credential handling | Backend | 3 | Backend Dev
| Backend Development | Connection pooling & retry | Backend | 4 | Backend Dev
| Backend Development | Dynamic query builder | Backend | 4 | Backend Dev
| Backend Development | Payload extraction logic | Backend | 3 | Backend Dev
| UI Development | DB connector screens | UI | 5 | UI Dev
| UI Development | API to DB mapping UI | UI | 4 | UI Dev
| QA Test Design | DB & query test cases | QA | 3 | QA
| QA Execution | Payload & transaction validation | QA | 4 | QA
Module 4: Test Case Management | Requirement Analysis | Test case screen & rules analysis | UI | 2 | UI Dev
| Design | Test case UI layout | UI | 3 | UI Dev
| Design | Test case persistence model | Backend | 3 | Backend Dev
| Backend Development | Test case CRUD & versioning | Backend | 6 | Backend Dev
| Backend Development | Header & payload persistence | Backend | 4 | Backend Dev
| Backend Development | API/DB connector mapping | Backend | 4 | Backend Dev
| UI Development | Input section UI | UI | 6 | UI Dev
| UI Development | Validation section UI | UI | 6 | UI Dev
| UI Development | Row add/remove logic | UI | 4 | UI Dev
| QA Test Design | Mandatory & rule validations | QA | 4 | QA
| QA Execution | Create/update/view/delete tests | QA | 6 | QA
Module 5: Bulk Test Case Import | Design | Bulk upload flow | UI | 2 | UI Dev
| Backend Development | CSV/Excel parser | Backend | 4 | Backend Dev
| Backend Development | Partial success & error handling | Backend | 3 | Backend Dev
| UI Development | Bulk upload UI | UI | 4 | UI Dev
| QA Test Design | Bulk scenarios | QA | 2 | QA
| QA Execution | Bulk validation & errors | QA | 3 | QA
Module 6: Test Execution Engine | Design | Execution orchestration flow | Backend | 4 | Backend Dev
| Backend Development | Execution request handler | Backend | 5 | Backend Dev
| Backend Development | Runtime ID generation | Backend | 3 | Backend Dev
| Backend Development | Payload & header placeholder replace | Backend | 4 | Backend Dev
| Backend Development | Parallel API execution | Backend | 6 | Backend Dev
| Backend Development | Execution persistence | Backend | 4 | Backend Dev
| QA Test Design | Execution scenarios | QA | 3 | QA
| QA Execution | Single/multi connector execution | QA | 5 | QA
| QA Execution | Retry & parallel validation | QA | 4 | QA
Module 7: Test Pack & Scheduling | Design | Pack & scheduling design | Backend | 2 | Backend Dev
| Backend Development | Pack CRUD APIs | Backend | 4 | Backend Dev
| Backend Development | Scheduler service | Backend | 4 | Backend Dev
| Backend Development | Retry failed logic | Backend | 3 | Backend Dev
| UI Development | Pack management UI | UI | 5 | UI Dev
| UI Development | Schedule configuration UI | UI | 4 | UI Dev
| QA Execution | Schedule & retry validation | QA | 4 | QA
Module 8: Validation Engine | Design | Validation rule definitions | Backend | 3 | Backend Dev
| Backend Development | API response validation | Backend | 4 | Backend Dev
| Backend Development | DB payload comparison | Backend | 5 | Backend Dev
| Backend Development | Intermediate/final state logic | Backend | 4 | Backend Dev
| UI Development | Side-by-side comparison UI | UI | 4 | UI Dev
| QA Execution | Validation accuracy tests | QA | 5 | QA
Module 9: HTML Report & Audit | Design | Report structure | UI | 2 | UI Dev
| Backend Development | Execution report persistence | Backend | 4 | Backend Dev
| Backend Development | Payload diff engine | Backend | 4 | Backend Dev
| UI Development | HTML report UI | UI | 5 | UI Dev
| QA Execution | Report accuracy & export | QA | 4 | QA
Module 10: Execution Dashboard | Design | Dashboard KPIs & metrics | UI | 2 | UI Dev
| Backend Development | Aggregation APIs | Backend | 4 | Backend Dev
| UI Development | Charts & summary cards | UI | 5 | UI Dev
| QA Execution | Dashboard data validation | QA | 4 | QA
Module 11: Test Coverage Dashboard | Design | Coverage rules | Backend | 2 | Backend Dev
| Backend Development | Coverage calculation APIs | Backend | 4 | Backend Dev
| UI Development | Coverage UI & filters | UI | 5 | UI Dev
| QA Execution | Coverage accuracy | QA | 4 | QA
Module 12: Configuration Screen | Design | Master data model | Backend | 2 | Backend Dev
| Backend Development | CRUD APIs for masters | Backend | 6 | Backend Dev
| UI Development | Master screens | UI | 6 | UI Dev
| UI Development | Search/filter/pagination | UI | 4 | UI Dev
| QA Execution | CRUD & RBAC validation | QA | 5 | QA