## Phase 2
Module | Task | Component | Dependency | Estimates (Days) | Resource | Planned Start Date | Planned End Date | Milestone
All Modules | Sample Input & Expected Output (UK – HSBC) | QA | HSBC SME Dependency | 5 | HSBC-SME | 06-Jan-2026
| UI Wireframe Design & Discussion | UI | Project Start | 9 | UX-1 | 06-Jan-2026
| Wireframe Review & Sign-off | UI | Wireframe Design | 4 | UX-1 | 15-Jan-2026 |  | UX Baseline Approved
| KT to New Resources | Cross-Team | Project Start | 5 | Tech Lead | 19-Jan-2026 |  | KT Completed
| Incorporate Review Comments | UI | Review Feedback | 2 | UX-1 | 23-Jan-2026
| Framework Design & Implementation | Backend/UI | UX Baseline Approved | 5 | BE-Dev-1 + UI-1 | 27-Jan-2026 |  | Framework Ready
Module 1: API Connector | System Analysis & Solution Design | Backend | Dev Start | 3 | BE-Dev-1 | 03-Feb-2026
| Connector Module Implementation | Backend | System Analysis | 10 | BE-Dev-1 | 06-Feb-2026
| Token Logic Implementation | Backend | Connector Impl | 4 | BE-Dev-2 | 10-Feb-2026
| API Connector UI | UI | UX Approved | 6 | UI-1 | 06-Feb-2026
| QA Scenario & Data Preparation | QA | API Ready | 4 | QA-1 | 07-Feb-2026
| QA Functional & Integration Testing | QA | UI Ready | 6 | QA-1 | 13-Feb-2026
| Backend Bug Fixing | Backend | QA Defects | 3 | BE-Dev-3 | 21-Feb-2026
| UI Bug Fixing | UI | QA Defects | 2 | UI-1 | 21-Feb-2026
| QA Bug Retest & Stabilization | QA | Bug Fixing | 2 | QA-2 | 24-Feb-2026 |  | Module 1 Complete
Module 2: DB Connector | System Analysis & Solution Design | Backend | Parallel | 3 | BE-Dev-2 | 06-Feb-2026
| DB Connector Backend & Pooling | Backend | System Analysis | 10 | BE-Dev-2 | 06-Feb-2026
| Token Logic Implementation | Backend | Connector Impl | 4 | BE-Dev-1 | 10-Feb-2026
| DB Connector UI | UI | UX Approved | 6 | UI-1 | 17-Feb-2026
| QA Test Case Design & Query Validation | QA | DB Backend Ready | 4 | QA-1 | 18-Feb-2026
| QA Functional & Data Accuracy Testing | QA | UI Ready | 6 | QA-1 | 24-Feb-2026
| Backend Bug Fixing | Backend | QA Defects | 3 | BE-Dev-3 | 03-Mar-2026
| UI Bug Fixing | UI | QA Defects | 2 | UI-1 | 03-Mar-2026
| QA Bug Retest & Regression | QA | Bug Fixing | 2 | QA-2 | 06-Mar-2026 |  | Module 2 Complete
Module 3: Test Case Management | Test Case CRUD & Versioning APIs | Backend | Module 2 | 20 | BE-Dev-1 | 24-Feb-2026
| Test Case Management UI | UI | UX Approved | 18 | UI-1 | 26-Feb-2026
| QA Test Case Design & Rule Matrix | QA | APIs Ready | 5 | QA-1 | 05-Mar-2026
| QA Functional & UI Validation | QA | UI Ready | 7 | QA-1 | 10-Mar-2026
| Backend Bug Fixing | Backend | QA Defects | 3 | BE-Dev-3 | 18-Mar-2026
| UI Bug Fixing | UI | QA Defects | 2 | UI-1 | 18-Mar-2026
| QA Bug Retest & Version Validation | QA | Bug Fixing | 3 | QA-2 | 20-Mar-2026 |  | Test Case Creation Ready
Module 4: Bulk Test Case Import | Import Template Design (CSV/Excel) | Backend | Test Case Ready | 5 | BE-Dev-1 | 23-Mar-2026
| Bulk Import Parser & Validation | Backend | Template Ready | 10 | BE-Dev-2 | 26-Mar-2026
| Bulk Import UI | UI | UX Approved | 8 | UI-1 | 26-Mar-2026
| QA Template Review & Data Prep | QA | Template Ready | 3 | QA-1 | 01-Apr-2026
| QA Bulk Import Functional Testing | QA | Parser Ready | 4 | QA-1 | 07-Apr-2026
| Backend Bug Fixing | Backend | QA Defects | 3 | BE-Dev-3 | 13-Apr-2026
| UI Bug Fixing | UI | QA Defects | 2 | UI-1 | 13-Apr-2026
| QA Bug Retest & Partial Success Validation | QA | Bug Fixing | 2 | QA-2 | 16-Apr-2026 |  | Module 4 Complete
Module 5: Test Execution Engine | Execution Engine Core Services | Backend | Module 4 Complete | 20 | BE-Dev-1 | 01-Apr-2026
| Execution Trigger & Status UI | UI | UX Approved | 12 | UI-1 | 07-Apr-2026
| QA Scenario Design (Execution Flow) | QA | Engine Core Ready | 4 | QA-1 | 10-Apr-2026
| QA Execution & Parallel Run Testing | QA | Trigger UI Ready | 7 | QA-1 | 15-Apr-2026
| Backend Bug Fixing | Backend | QA Defects | 3 | BE-Dev-3 | 24-Apr-2026
| UI Bug Fixing | UI | QA Defects | 2 | UI-1 | 24-Apr-2026
| QA Bug Retest & Stability Validation | QA | Bug Fixing | 4 | QA-2 | 28-Apr-2026 |  | Module 5 Complete
Module 6: Validation Engine | Validation Rule Engine & DB Compare | Backend | Module 5 Stable | 14 | BE-Dev-2 | 18-Apr-2026
| QA Rule Coverage & Expected Data Prep | QA | Rule Engine Ready | 4 | QA-1 | 24-Apr-2026
| QA Validation Accuracy Testing | QA | Rule Coverage Ready | 4 | QA-1 | 30-Apr-2026
| Backend Bug Fixing | Backend | QA Defects | 3 | BE-Dev-3 | 06-May-2026
| UI Bug Fixing | UI | QA Defects | 2 | UI-1 | 06-May-2026
| QA Bug Retest & Rule Stabilization | QA | Bug Fixing | 4 | QA-2 | 09-May-2026 |  | Module 6 Complete
Module 7: Test Pack & Scheduling | Scheduler & Pack Mapping APIs | Backend | Validation Stable | 10 | BE-Dev-2 | 22-Apr-2026
| Test Pack UI & Scheduling | UI | UX Approved | 8 | UI-1 | 25-Apr-2026
| QA Scheduling Scenario Design | QA | Pack UI Ready | 3 | QA-1 | 30-Apr-2026
| QA Schedule Execution Testing | QA | Scenario Ready | 3 | QA-1 | 05-May-2026
| Backend Bug Fixing | Backend | QA Defects | 3 | BE-Dev-3 | 09-May-2026
| UI Bug Fixing | UI | QA Defects | 2 | UI-1 | 09-May-2026
| QA Bug Retest & Retry Validation | QA | Bug Fixing | 2 | QA-2 | 13-May-2026 |  | Module 7 Complete
Module 8: HTML Report & Audit | HTML Report & Audit APIs | Backend | Scheduling Stable | 10 | BE-Dev-1 | 28-Apr-2026
| Report View UI & Export | UI | UX Approved | 8 | UI-1 | 30-Apr-2026
| QA Report Structure & Data Mapping | QA | API Ready | 3 | QA-1 | 05-May-2026
| QA Report Functional & Export Testing | QA | UI Ready | 3 | QA-1 | 08-May-2026
| Backend Bug Fixing | Backend | QA Defects | 3 | BE-Dev-3 | 11-May-2026
| UI Bug Fixing | UI | QA Defects | 2 | UI-1 | 11-May-2026
| QA Bug Retest & Audit Validation | QA | Bug Fixing | 5 | QA-2 | 14-May-2026 |  | Module 8 Complete
Module 9: Execution Dashboard | Execution Aggregation APIs | Backend | Reports Ready | 10 | BE-Dev-2 | 15-May-2026
| Execution Dashboard UI | UI | UX Approved | 8 | UI-1 | 18-May-2026
| QA Dashboard Metric Validation | QA | API Ready | 3 | QA-1 | 22-May-2026
| QA Dashboard UI & Data Testing | QA | UI Ready | 3 | QA-1 | 26-May-2026
| Backend Bug Fixing | Backend | QA Defects | 3 | BE-Dev-3 | 27-May-2026
| UI Bug Fixing | UI | QA Defects | 2 | UI-1 | 27-May-2026
| QA Bug Retest & Trend Validation | QA | Bug Fixing | 2 | QA-2 | 29-May-2026 |  | Module 9 Complete
Module 10: Test Coverage Dashboard | Coverage Calculation APIs | Backend | Test Case Ready | 8 | BE-Dev-1 | 20-May-2026
| Coverage Dashboard UI | UI | UX Approved | 8 | UI-1 | 23-May-2026
| QA Coverage Rule Mapping Review | QA | API Ready | 3 | QA-1 | 28-May-2026
| QA Coverage Accuracy Testing | QA | UI Ready | 3 | QA-1 | 01-Jun-2026
| Backend Bug Fixing | Backend | QA Defects | 3 | BE-Dev-3 | 03-Jun-2026
| UI Bug Fixing | UI | QA Defects | 2 | UI-1 | 03-Jun-2026
| QA Bug Retest & Coverage Stabilization | QA | Bug Fixing | 2 | QA-2 | 05-Jun-2026 |  | Coverage Ready
Module 11: Health Check & Monitoring | Health Check API Design | Backend | Mid-May Start | 3 | Tech Lead | 22-May-2026
| Service-Level Health APIs | Backend | API Design | 7 | BE-Dev-2 | 26-May-2026
| Health Status UI | UI | UX Approved | 5 | UI-1 | 29-May-2026
| QA Health Scenario Design | QA | API Ready | 2 | QA-1 | 02-Jun-2026
| QA Health Check Validation | QA | Scenario Ready | 4 | QA-2 | 04-Jun-2026 |  | Health Check Ready
Module 12: User Management & Security | Auth Strategy & RBAC Design | Backend | Parallel | 5 | Tech Lead | 27-May-2026
| Auth APIs & Middleware | Backend | RBAC Design | 18 | BE-Dev-1 | 30-May-2026
| User / Role / Login UI | UI | UX Approved | 15 | UI-1 | 02-Jun-2026
| QA Scenario & Test Case Design | QA | API Ready | 5 | QA-1 | 06-Jun-2026
| QA Functional Testing | QA | UI Ready | 7 | QA-1 | 10-Jun-2026
| Backend Bug Fixing | Backend | QA Defects | 3 | BE-Dev-3 | 15-Jun-2026
| UI Bug Fixing | UI | QA Defects | 2 | UI-1 | 15-Jun-2026
| QA Bug Retest & Regression | QA | Bug Fixing | 3 | QA-2 | 17-Jun-2026 |  | Module 12 Complete
Module 13: Configuration Master Data | Master Data CRUD & RBAC APIs | Backend | Module 12 Ready | 12 | BE-Dev-2 | 02-Jun-2026
| Configuration Screens UI | UI | UX Approved | 10 | UI-1 | 06-Jun-2026
| QA Master Data Scenario Design | QA | API Ready | 3 | QA-1 | 11-Jun-2026
| QA CRUD & RBAC Validation | QA | UI Ready | 3 | QA-1 | 13-Jun-2026
| Backend Bug Fixing | Backend | QA Defects | 3 | BE-Dev-3 | 17-Jun-2026
| UI Bug Fixing | UI | QA Defects | 2 | UI-1 | 17-Jun-2026
| QA Bug Retest & Regression | QA | Bug Fixing | 2 | QA-2 | 19-Jun-2026 |  | Module 13 Complete
All Modules | Pre-Regression Smoke Test using Health APIs | QA | Health Ready | 3 | QA-2 | 21-Jun-2026 |  | Smoke Test Passed
| End-to-End Regression & Go-Live | QA | All Stable | 8 | QA-1 + QA-2 | 21-Jun-2026 |  | Go-Live

## Holidays
Holiday Date
01-Jan-2026
26-Jan-2026
04-Mar-2026
01-May-2026